## Summary
PWC data center applications/projects - summary
Pulled live 2026-10-15 13:23 ET from gisweb.pwcva.gov (Build_Out_Analysis layers 9/10, CountyMapper pending cases layer 2, Zoning layer 6) and ePortal (egcss.pwcgov.org).
Stage | Projects | Campus-layer rows | Planned GFA (sf, campus layer) | Acreage (GIS, where available)
Under Construction | 13 | 13 | 16588254 | 957.2
Completed | 10 | 10 | 5358580 | 342.2
Approved / Planned | 42 | 42 | 39260057 | 2090.3
Pending / Under Review | 11 | 10 | 14680648 | 941.8
In Planning Office (site plan in review) | 2 | 0 | 0 | 0
Denied | 2 | 2 | 10700000 | 875.6
Void / Withdrawn / Denied | 8 | 1 | 11555200 | 884.2
TOTAL
County raw status (campus layer 10) | Campuses
Planned | 53
Pending | 15
Completed | 10
Buildings (layer 9) by status shown (county label in county_layer_status) | Buildings
Planned | 91
Pending | 31
Denied | 37
Completed | 59
Under Construction | 29
Notes
One row per campus (78 in layer 10; some share a case number) plus ePortal-only projects not in the campus layer (10).
Buildings joined to campuses by spatial point-in-polygon (all 247 fall in exactly one campus); building PlanningCaseNumber disagrees with campus case number for 21 (see Buildings sheet).
Stage rules: plan section 5. Precedence Under Construction > county campus status. Completed = campus ProjectStatus Completed. Planned -> Approved / Planned. Pending -> Pending / Under Review (sub-state in county_status_pending_case, e.g. Deferred, Suspended).
Denied (Oct 15, 2026 edit): Digital Gateway North/South (REZ2022-00032/-33) stage set to 'Denied' and Compass (REZ2022-00036) kept as 'Void / Withdrawn / Denied' (no evidence found it was denied). The 37 buildings of all three (12+8+17) show BuildingStatus 'Denied' (per Patrick: Digital Gateway denied; Compass buildings shown with them); the county layer label ('Pending') is kept in Buildings.county_layer_status. The county pending-case layer still lists the three as Suspended (On-Hold).
Pending-case layer: 9 'DATA CENTER' description matches included (7 by campus case number; SUP2026-00035 and SUP2027-00008 attached to Southgate South and Gardner Property by project name). Other pending-layer companion cases joined by case number or exact name.
ePortal 'data center' keyword search (1,094 hits, noisy) joined by case number, then building GPIN, then case number cited in description, then exact/unique-prefix name. Join method is shown per case in eportal_related_cases.
ePortal-only rows: stage from ePortal case status; acreage/district filled only if the case is also in the pending-case layer; otherwise blank. Public facility (substation) reviews excluded.
Blank = not available in the sources. MW, applicant/owner not in these sources.
last_edit_date = latest LastEditDate among campus and its buildings (county GIS edit, not filing date).

## Projects
row_id | project_name | buildings | county_project_name | primary_case_number | all_case_numbers | stage | county_status_campus_layer | county_status_pending_case | eportal_status_primary_case | stage_basis | acreage | planned_gfa_sf | remaining_gfa_sf | buildings_count | building_status_counts | buildings_gfa_sum_sf | magisterial_district | in_dc_overlay_dcood | zoning_district | gpins | addresses | buildings | building_permit_cases | pending_case_layer_cases | use_permit_cases | eportal_related_cases | site_plans_in_review | energov_id | source_layer | source_url | last_edit_date | notes
1 | Amazon Village Place Technology Park | 4 | Village Place Technology Park | REZ2020-00024 | REZ2020-00024; SUP2020-00037 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 45.18 | 978169 | 978169 | 4 | Under Construction: 4 | 217917 | Gainesville | No | PMD | 7397-35-5597; 7397-35-8363; 7397-36-1468; 7397-36-2834 | 14435 JOHN MARSHALL HWY; 14455 JOHN MARSHALL HWY; 14475 JOHN MARSHALL HWY; 14495 JOHN MARSHALL HWY | Village Place Technology Park Bldg 1 (Under Construction); Village Place Technology Park Bldg 2 (Under Construction); Village Place Technology Park Bldg 3 (Under Construction); Village Place Technology Park Bldg 4 (Under Construction) | BLD2023-01296 (Issued); BLD2023-04861 (Issued); BLD2023-07720 (Issued); BLD2024-03062 (Issued) |  | SUP2020-00037 [SUP; ACTIVE; approved 2021-06-14] | REZ2020-00024 [Rezoning - Proffer Amendment; Approved; case number]; SUP2020-00037 [Special Use Permit - New Application; Approved; case number REZ2020-00024 referenced in description] |  | 1ea11347-1c8b-4847-b1a4-76194692023c | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); Planning/Zoning/6 (use permits); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/35?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
2 | CloudHQ Manassas Corporate Center (MCC) | 9 | Airport Gateway Commerce Center I | PLN2011-00437 | PLN2011-00437; REZ2024-00025 | Under Construction | Planned |  | Amended | Rule 1: >=1 building 'Under Construction' in layer 9 | 178.45 | 2326576 | 1518452 | 9 | Completed: 2; Planned: 5; Under Construction: 2 | 2930147 | Coles | Yes | M/T PBD | 7694-84-2446; 7694-85-3066; 7694-87-2108; 7694-87-3694; 7694-95-2326; 7694-95-7303; 7694-96-2732; 7794-06-4463 | 10100 HARRY J PARRISH BLVD; 10105 HARRY J PARRISH BLVD; 10740 AIRMAN AVE; 10849 AIRMAN AVE; 10880 AIRMAN AVE; 10900 AIRMAN AVE; 10910 AIRMAN AVE; 10940 AIRMAN AVE | CloudHQ Manassas Corporate Center 1 (Completed); CloudHQ Manassas Corporate Center 2 (Completed); CloudHQ Manassas Corporate Center 3 (Planned); CloudHQ Manassas Corporate Center 4 (Planned); CloudHQ Manassas Corporate Center 5 (Planned); CloudHQ Manassas Corporate Center 6A (Under Construction); CloudHQ Manassas Corporate Center 6B (Planned); CloudHQ Manassas Corporate Center 6C (Planned); CloudHQ Manassas Corporate Center 7 (Under Construction) | BLD2016-05888 (Finaled); BLD2019-02023 (Finaled); BLD2020-04041 (Issued); BLD2026-04432 (Issued) |  |  | PLN2011-00437 [Rezoning - Proffer Amendment; Amended; case number]; REZ2024-00025 [Rezoning - Proffer Amendment; Approved; case number]; SPR2016-00304 [Site Plan - Final; Approved; GPIN (building parcel)]; SPR2017-00173 [Site Plan - Revision; Approved; GPIN (building parcel)]; SPR2017-00417 [Site Plan - Revision; Approved; GPIN (building parcel)]; SPR2018-00088 [Site Plan - Asbuilt Plan; Approved; GPIN (building parcel)]; SPR2024-00380 [Site Plan - Final; Approved; GPIN (building parcel)] |  | 9ad88838-f931-4013-b253-716e33117c14 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/30?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
3 | CloudHQ Manassas Data Center (MDC) | 3 | Ashwood Addition | REZ2018-00001 | REZ2018-00001; REZ2023-00025 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 85.4 | 1644498 | 1644498 | 3 | Under Construction: 3 | 1644249 | Coles | Yes | M-2 | 7695-41-6086; 7695-50-2882; 7695-50-9420 | 10430 HARRY J PARRISH BLVD; 10450 HARRY J PARRISH BLVD; 10470 HARRY J PARRISH BLVD | CloudHQ Manassas Data Center 1 (Under Construction); CloudHQ Manassas Data Center 2 (Under Construction); CloudHQ Manassas Data Center 3 (Under Construction) | BLD2025-04928 (Issued); BLD2026-01701 (Issued); BLD2026-02951 (Issued) |  |  | REZ2018-00001 [Rezoning - Proffer Amendment; Approved; case number]; REZ2023-00025 [Rezoning - Proffer Amendment; Withdrawn; case number REZ2018-00001 referenced in description] |  | bac2c975-6f9e-462c-a9f0-d855015bd869 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/29?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
4 | Digital Realty | 2 | Brickyard | REZ2018-00002 | REZ2018-00002 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 61.47 | 1602558 | 802135 | 2 | Completed: 1; Under Construction: 1 | 1617620 | Coles | Yes | M-1 | 7695-53-6537; 7695-53-9602 | 10050 BRICKYARD WAY; 10051 BRICKYARD WAY | DLR IAD-50 (Under Construction); DLR IAD-51 (Completed) | BLD2024-02491 (Finaled); BLD2025-02545 (Issued) |  |  | REZ2018-00002 [Rezoning - Proffer Amendment; Approved; case number] |  | 5b9b1adb-eadd-43e0-aa7f-4fe0a600d4f2 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/28?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
5 | George Mason Research Park | 3 | NVA05A & NVA05B Proffer Amendment | REZ2024-00009 | REZ2024-00009; REZ2024-00042 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 46.18 | 711418 | 440878 | 3 | Completed: 1; Under Construction: 2 | 711418 | Brentsville | Yes | PBD | 7696-30-4783; 7696-31-9262; 7696-41-6854 | 8930 WELLINGTON RD; 9001 FREEDOM CENTER BLVD; 9101 FREEDOM CENTER BLVD | Stack Northern Virginia NVA05A (Completed); Stack Northern Virginia NVA05B (Under Construction); Stack Northern Virginia NVA05C (Under Construction) | BLD2023-00562 (Finaled); BLD2025-03019 (Issued); BLD2025-03129 (Issued) |  |  | REZ2024-00009 [Rezoning - Proffer Amendment; Approved; case number]; REZ2024-00042 [Rezoning - Non-Residential; Approved; case number] |  | 19004ff1-7e88-4661-9d3f-ad33ecaa1da2 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/22?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
6 | Manassas Tech Center | 3 | Manassas Tech Center PRA | REZ2026-00022 | REZ2026-00022 | Under Construction | Pending |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 40.41 | 696554 | 696554 | 3 | Planned: 2; Under Construction: 1 | 686721 | Brentsville | Yes | PBD PMD | 7596-61-8378; 7596-62-9148 | 8880 MIKE GARCIA DR; 8881 MIKE GARCIA DR; 8890 MIKE GARCIA DR | Manassas Tech Center Building A (Under Construction); Manassas Tech Center Building B (Planned); Manassas Tech Center Building C (Planned) | BLD2025-00144 (Issued); BLD2026-06372 (Planned) |  |  | REZ2026-00022 [Rezoning - Proffer Amendment; Approved; case number] |  | 7bbe6460-60e2-41f9-99a4-a5e725b52010 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/16?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25 | Campus case is county-Pending but a building is Under Construction (stage per rule 1); ePortal shows primary case Approved while campus layer says Pending (county data conflict)
7 | Microsoft Azure Gainesville Tech Park | 4 | Gainesville Tech Park | REZ2020-00011 | REZ2020-00011 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 83.13 | 1245499 | 1245499 | 4 | Planned: 3; Under Construction: 1 | 1430352 | Brentsville | Yes | M-2 | 7496-88-1217 | 13060 HANSEN FARM RD; 13062 HANSEN FARM RD; 13064 HANSEN FARM RD; 13066 HANSEN FARM RD | Microsoft Azure MNZ03 (Under Construction); Microsoft Azure MNZ04 (Planned); Microsoft Azure MNZ05 (Planned); Microsoft Azure MNZ06 (Planned) | <Null> (Planned); BLD2023-07492 (Issued); BLD2025-02384 (Planned) |  |  | REZ2020-00011 [Rezoning - Non-Residential; Approved; case number] |  | 01fffe17-1fdc-46e3-bd5c-f5795320e7e6 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/5?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
8 | NTT Grove at Gainesville | 4 | I-66 & Route 29 Technology Park | REZ2021-00001 | REZ2021-00001; SUP2021-00002 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 90.9 | 2279176 | 2279176 | 4 | Planned: 1; Under Construction: 3 | 2279176 | Gainesville | No | B-1 | 7397-56-8403 | 7151 CATHARPIN RD; 7250 GROVE HILL BLVD; 7251 GROVE HILL BLVD; 7253 GROVE HILL BLVD | NTT Grove at Gainesville VA10 (Under Construction); NTT Grove at Gainesville VA11 (Under Construction); NTT Grove at Gainesville VA12 (Under Construction); NTT Grove at Gainesville VA13 (Planned) | BLD2023-05471 (Issued); BLD2025-04670 (Issued); BLD2026-05831 (Issued) |  | SUP2021-00002 [SUP; ACTIVE; approved 2021-12-06] | REZ2021-00001 [Rezoning - Proffer Amendment; Approved; case number]; SPR2026-00342 [Site Plan - Revision; Approved; GPIN (building parcel)]; SUP2021-00002 [Special Use Permit - New Application; Approved; case number REZ2021-00001 referenced in description] |  | 4f041cf7-c8de-4afd-a4e3-f12ba520a0cd | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); Planning/Zoning/6 (use permits); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/34?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
9 | Project Gainesville | 4 | BOCS-ARC | REZ1958-0021 | REZ1958-0021; SUP2023-00006 | Under Construction | Planned |  |  | Rule 1: >=1 building 'Under Construction' in layer 9 | 58.54 | 943981 | 943981 | 4 | Under Construction: 4 | 943981 | Brentsville | Yes | M-1 | 7497-41-7199 | 7675 DEACON FALLS DR; 7701 DEACON FALLS DR; 7725 DEACON FALLS DR; 7751 DEACON FALLS DR | Amazon AWS IAD A (Under Construction); Amazon AWS IAD B (Under Construction); Amazon AWS IAD C (Under Construction); Amazon AWS IAD D (Under Construction) | BLD2022-05922 (Issued); BLD2024-05622 (Issued); BLD2026-00592 (Issued); BLD2026-00593 (Issued) |  |  | SUP2023-00006 [Special Use - Modification to Development Standards; Withdrawn; GPIN (building parcel)] |  | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/83?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
10 | QTS Manassas 1 | 6 | IBM | REZ1980-0030 | REZ1980-0030; REZ2020-00019; REZ2023-00002 | Under Construction | Planned |  |  | Rule 1: >=1 building 'Under Construction' in layer 9 | 109.36 | 1356387 | 515582 | 6 | Completed: 4; Under Construction: 2 | 1356387 | Brentsville | Yes | M-2 PBD | 7695-38-4851; 7695-39-0644; 7695-47-3376; 7695-48-1668; 7695-48-5650; 7695-58-1491 | 9301 FREEDOM CENTER BLVD; 9351 FREEDOM CENTER BLVD; 9400 GODWIN DR; 9420 GODWIN DR; 9450 GODWIN DR; 9540 GODWIN DR | QTS Manassas DC1 (Completed); QTS Manassas DC2 (Completed); QTS Manassas DC3 (Completed); QTS Manassas DC4 (Under Construction); QTS Manassas DC5 (Completed); QTS Manassas DC6 (Under Construction) | BLD2018-06634 (Finaled); BLD2021-04300 (Finaled); BLD2022-06119 (Finaled); BLD2023-04643 (Finaled); BLD2024-06788 (Issued); BLD2025-03459 (Issued) |  |  | REZ2020-00019 [Rezoning - Non-Residential; Approved; case number]; REZ2023-00002 [Rezoning - Proffer Amendment; Approved; case number] |  | 81cc348e-ba85-4c9b-9dc9-2a31c19aa522 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/23?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
11 | South Point Phase II | 2 | South Point Phase II | REZ2020-00021 | REZ2020-00021 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 22.22 | 530000 | 399966 | 2 | Completed: 1; Under Construction: 1 | 482934 | Brentsville | Yes | M-2 | 7596-16-5979; 7596-27-0053 | 8300 BUCKEYE TIMBER DR; 8400 BUCKEYE TIMBER DR | South Point Phase II Building A (Completed); South Point Phase II Building B (Under Construction) | BLD2024-01532 (Finaled); BLD2025-00827 (Issued) |  |  | REZ2020-00021 [Rezoning - Proffer Amendment; Approved; case number] |  | 50945ad4-3eb2-48ff-be0f-fbede2cfd419 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/13?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
12 | Stack Infrastructure NVA02 Manassas | 7 | Avanti at Innovation PRA | REZ2019-00028 | REZ2019-00028 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 86.11 | 1559831 | 553730 | 7 | Completed: 5; Under Construction: 2 | 1191904 | Brentsville | Yes | PBD | 7595-65-9789; 7595-75-3611; 7595-76-2590; 7595-76-6544; 7595-85-3742; 7595-85-6929 | 9530 HORNBAKER RD; 9570 HORNBAKER RD; 9590 HORNBAKER RD; 9640 HORNBAKER RD; 9730 HORNBAKER RD; 9740 HORNBAKER RD; 9750 HORNBAKER RD | Stack Northern Virginia NVA02A (Completed); Stack Northern Virginia NVA02B (Completed); Stack Northern Virginia NVA02C (Completed); Stack Northern Virginia NVA02D (Completed); Stack Northern Virginia NVA02E (Completed); Stack Northern Virginia NVA02F (Under Construction); Stack Northern Virginia NVA02G (Under Construction) | BLD2021-02881 (Finaled); BLD2022-00534 (Finaled); BLD2022-01720 (Finaled); BLD2022-07412 (Finaled); BLD2023-03853 (Finaled); BLD2024-05348 (Issued); BLD2025-01136 (Issued) |  |  | REZ2019-00028 [Rezoning - Proffer Amendment; Approved; case number]; SPR2020-00363 [Site Plan - Final; Approved; name exact] |  | 08eefd48-2ab4-438d-9d00-e80397055cff | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/47?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
13 | Stack Infrastructure NVA02 YFT | 3 | Youth For Tomorrow | REZ2019-00034 | REZ2019-00034 | Under Construction | Planned |  | Approved | Rule 1: >=1 building 'Under Construction' in layer 9 | 49.84 | 713607 | 713607 | 3 | Under Construction: 3 | 713492 | Brentsville | No | PBD | 7595-54-7478 | 10155 LINTON HALL RD; 10161 LINTON HALL RD; 10167 LINTON HALL RD | Stack Northern Virginia NVA02H (Under Construction); Stack Northern Virginia NVA02I (Under Construction); Stack Northern Virginia NVA02J (Under Construction) | BLD2025-03391 (Issued); BLD2025-06092 (Issued); BLD2026-01905 (Issued) |  |  | REZ2019-00034 [Rezoning - Non-Residential; Approved; case number]; SPR2025-00355 [Site Plan - Revision; Approved; name exact]; SPR2027-00080 [Site Plan - Administrative Review; Pending; GPIN (building parcel)] | SPR2027-00080 (Pending) | 222f06a0-c603-4233-9289-74ff5439b34d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/46?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
14 | Amazon Bethlehem Technology Park | 4 | Bethlehem Technology Park Rezoning | REZ2016-00024 | REZ2016-00024 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 61.55 | 740000 | 0 | 4 | Completed: 4 | 719742 | Brentsville | Yes | M-2 | 7596-58-8732 | 8180 BETHLEHEM RD; 8190 BETHLEHEM RD; 8200 BETHLEHEM RD; 8210 BETHLEHEM RD | Amazon Bethlehem Technology Park DC18 (Completed); Amazon Bethlehem Technology Park DC19 (Completed); Amazon Bethlehem Technology Park DC20 (Completed); Amazon Bethlehem Technology Park DC23 (Completed) | BLD2016-06361 (Finaled); BLD2017-01263 (Finaled); BLD2017-02845 (Finaled); BLD2018-03269 (Finaled) |  |  |  |  | b85539e6-a3d5-42c6-9c56-413bf113335d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/14?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
15 | Amazon Freedom Boulevard | 2 | Amazon AWS IAD - Freedom Campus | REZ1989-0022 | REZ1989-0022 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 18.75 | 409252 | 0 | 2 | Completed: 2 | 408422 | Brentsville | Yes | M-2 | 7696-21-7764 | 9020 FREEDOM CENTER BLVD; 9040 FREEDOM CENTER BLVD | Amazon AWS IAD-130 (Completed); Amazon AWS IAD-131 (Completed) | BLD2019-01155 (Finaled); BLD2019-04018 (Finaled) |  |  |  |  | 3ce1ec8d-e4fb-4b8b-9387-14d85dccd570 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/21?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
16 | Amazon Mason King Court | 3 | Wheeler Smith Wood Solite | REZ1969-0021 | REZ1969-0021 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 17.27 | 259543 | 0 | 3 | Completed: 3 | 376124 | Gainesville | Yes | M-1 | 7597-62-3841; 7597-72-1867 | 7505 MASON KING CT; 7510 MASON KING CT; 7610 MASON KING CT | Amazon AWS IAD-11 (Completed); Amazon AWS IAD-24 (Completed); Amazon AWS IAD-7 (Completed) | BLD2009-02929 (Finaled); BLD2012-02503 (Finaled); BLD2012-03056 (Finaled) |  |  | SPR2022-00356 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2023-00091 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2023-00092 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2023-00249 [Site Plan - Minor; Approved; GPIN (building parcel)] |  | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/39?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
17 | Amazon Midwood Center | 5 | Midwood Center | PLN2003-00108 | PLN2003-00108 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 66.81 | 689469 | 0 | 5 | Completed: 5 | 689469 | Gainesville | No | M-2 PBD | 7298-41-4524; 7298-51-5907 | 15395 JOHN MARSHALL HWY; 15445 JOHN MARSHALL HWY; 15455 JOHN MARSHALL HWY; 15465 JOHN MARSHALL HWY; 15475 JOHN MARSHALL HWY | Amazon AWS IAD 15445 John Marshall (Completed); Amazon AWS IAD-55 (Completed); Amazon AWS IAD-64 (Completed); Amazon AWS IAD-64 Ext (Completed); Amazon AWS IAD-84 (Completed) | BLD2014-01766 (Finaled); BLD2016-04280 (Finaled); BLD2018-06209 (Finaled); BLD2020-04888 (Finaled); BLD2022-07765 (Finaled) |  |  | SPR2015-20042 [Site Plan - Administrative Review; Approved; GPIN (building parcel)]; SPR2016-00217 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2017-00050 [Site Plan - Revision; Approved; name prefix (unique)]; SPR2017-00060 [Site Plan - Revision; Approved; GPIN (building parcel)]; SPR2017-00196 [Site Plan - Administrative Review; Approved; GPIN (building parcel)]; SPR2017-00337 [Site Plan - Revision; Closed; GPIN (building parcel)]; SPR2019-00255 [Site Plan - Revision; Approved; name prefix (unique)]; SPR2020-00038 [Site Plan - Administrative Review; Approved; GPIN (building parcel)]; SPR2023-00090 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2023-00423 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2024-00340 [Site Plan - Minor; Approved; GPIN (building parcel)] |  | 3861bb53-127d-425e-85de-cd895072e240 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/37?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
18 | Amazon Tanner Way | 4 | Brickyard | REZ2018-00002 | REZ2018-00002 | Completed | Completed |  | Approved | Rule 2: campus ProjectStatus Completed | 82.58 | 1798534 | 0 | 4 | Completed: 4 | 795191 | Coles | Yes | M-1 | 7695-62-8723 | 10261 TANNER WAY; 10281 TANNER WAY; 10301 TANNER WAY; 10321 TANNER WAY | Amazon AWS IAD-100 (Completed); Amazon AWS IAD-101 (Completed); Amazon AWS IAD-102 (Completed); Amazon AWS IAD-103 (Completed) | BLD2020-00115 (Finaled); BLD2020-04380 (Finaled); BLD2020-05182 (Finaled); BLD2021-00330 (Finaled) |  |  | REZ2018-00002 [Rezoning - Proffer Amendment; Approved; case number]; SPR2024-00173 [Site Plan - Revision; Approved; GPIN (building parcel)] |  | 5b9b1adb-eadd-43e0-aa7f-4fe0a600d4f2 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/27?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
19 | Amazon Thomasson Barn | 2 | Innovation at PW | PLN2007-00535 | PLN2007-00535 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 21.14 | 352530 | 0 | 2 | Completed: 2 | 352030 | Brentsville | Yes | PBD | 7595-95-6147 | 11150 THOMASSON BARN RD; 11200 THOMASSON BARN RD | Manassas Amazon AWS 139 (Completed); Manassas Amazon AWS 140 (Completed) | BLD2019-01459 (Finaled); BLD2019-02581 (Finaled) |  |  | SPR2023-00084 [Site Plan - Minor; Approved; GPIN (building parcel)] |  | 65a47980-e01f-4e3d-bc5c-e3f7c6c096f4 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/31?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-10-02
20 | Amazon Wellington South | 2 | Wellington South | REZ1989-0069 | REZ1989-0069 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 26.24 | 297160 | 0 | 2 | Completed: 2 | 297160 | Brentsville | Yes | M-2 | 7596-17-3979 | 7060 WELLINGTON RD; 7070 WELLINGTON RD | Amazon AWS IAD-73 Manassas (Completed); Amazon AWS IAD-74 Manassas (Completed) | BLD2015-22325 (Finaled); BLD2015-23921 (Finaled) |  |  | SPR2023-00086 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2027-00035 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00035 (Pending) | 3e7c27b9-d412-4ed3-9db7-33be4a5706d8 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/12?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
21 | CloudHQ Manassas Hornbaker | 1 | Innovation at PW | PLN2007-00535 | PLN2007-00535 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 19.44 | 223127 | 0 | 1 | Completed: 1 | 247608 | Brentsville | Yes | PBD | 7595-96-0662 | 9651 HORNBAKER RD | Manassas Amazon AWS 004 (Completed) | BLD2007-04468 (Finaled) |  |  | SPR2016-00013 [Site Plan - Asbuilt Plan; Approved; GPIN (building parcel)]; SPR2016-00204 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2020-00179 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2020-00384 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2024-00063 [Site Plan - Minor; Approved; GPIN (building parcel)]; SPR2026-00375 [Site Plan - Revision; Pending; GPIN (building parcel)] | SPR2026-00375 (Pending) | 65a47980-e01f-4e3d-bc5c-e3f7c6c096f4 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/26?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-10-02
22 | TPC Data Centers | 1 | 8765 and 8819 Wellington Road PRA | REZ2024-00008 | REZ2024-00008 | Completed | Completed |  | Approved | Rule 2: campus ProjectStatus Completed | 8.11 | 361500 | 0 | 1 | Completed: 1 | 361500 | Brentsville | Yes | M-2 | 7696-42-1559 | 8819 WELLINGTON RD | TPC Data Centers (Completed) | BLD2024-04783 (Finaled) |  |  | PLT2025-00063 [Plat Easement; Approved; GPIN (building parcel)]; REZ2024-00008 [Rezoning - Proffer Amendment; Approved; case number] |  | 55087cda-4790-4f98-be5d-2a054fe2c464 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/19?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
23 | Verizon Manassas 7777 Infantry Ridge | 1 | Battlefield Business Park | REZ1988-0030 | REZ1988-0030 | Completed | Completed |  |  | Rule 2: campus ProjectStatus Completed | 20.33 | 227465 | 0 | 1 | Completed: 1 | 227465 | Gainesville | Yes | PBD | 7697-47-3772 | 7777 INFANTRY RIDGE RD | Verizon Manassas 7777 Infantry Ridge (Completed) | BLD2026-02975 (Finaled) |  |  | SPR2023-00302 [Site Plan - Minor; Approved; GPIN (building parcel)] |  | 67ae5cc3-3e5f-439d-aa9f-b079257e7927 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/45?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
24 | 5451 Wellington Road East | 1 | ATLANTIC RESEARCH | REZ1958-0021 | REZ1958-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 7.45 | 116550 | 116550 | 1 | Planned: 1 | 116550 | Brentsville | Yes | M-1 | 7497-13-3597 | 5551 WELLINGTON RD GAINESVILLE, VA 20155 | Wellington Road East (Planned) |  |  |  | SPR2026-00322 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00322 (Pending) | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/561?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
25 | 5451 Wellington Road West | 1 | ATLANTIC RESEARCH | REZ1958-0021 | REZ1958-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 18 | 255500 | 255500 | 1 | Planned: 1 | 255500 | Brentsville | Yes | M-1 | 7497-04-7126 | 5451 WELLINGTON RD GAINESVILLE, VA 20155 | Wellington Road West (Planned) | [5 empty] | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/85?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
26 | Aligned Manassas | 1 | Blackburn Land Bay 5 | REZ2019-00022 | REZ2019-00022 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 28.36 | 1275141 | 432742 | 1 | Planned: 1 | 432742 | Gainesville | Yes | PMD | 7597-95-8953 | 10920 BALLS FORD RD | Aligned Data Centers IAD05 (Planned) |  |  |  | REZ2019-00022 [Rezoning - Proffer Amendment; Approved; case number] |  | bbbe6bc1-1a71-4b91-a844-a742a14e031d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/38?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
27 | Amazon Colchester Industrial Park | 2 | Mid-County Industrial Park | REZ2024-00006 | REZ2024-00006 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 64.11 | 664715 | 664715 | 2 | Planned: 2 | 448346 | Coles | Yes | M-2 M/T | 7991-45-0874 | 14901 DUMFRIES RD | Amazon Colchester Industrial Park 1 (Planned); Amazon Colchester Industrial Park 2 (Planned) |  |  |  | REZ2024-00006 [Rezoning - Non-Residential; Approved; case number]; SPR2026-00297 [Site Plan - Final; Pending; name exact] | SPR2026-00297 (Pending) | 3dd0c08d-d7fa-483c-8e0f-1913eb303cd0 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/32?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
28 | Amazon Innovation Drive | 5 | Eli Lilly at Innovation | PLN2007-00749 | PLN2007-00749; PLN2007-0074 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 78.39 | 1087901 | 201000 | 5 | Completed: 4; Planned: 1 | 1087901 | Brentsville | Yes | PBD | 7695-17-9607; 7695-26-4469; 7695-26-7645; 7695-36-1324 | 9670 INNOVATION DR; 9680 INNOVATION DR; 9700 INNOVATION DR; 9720 INNOVATION DR; 9740 INNOVATION DR | Amazon AWS IAD-104 (Completed); Amazon AWS IAD-105 (Completed); Amazon AWS IAD-106 (Completed); Amazon AWS IAD-107 (Completed); Amazon AWS IAD-F (Planned) | BLD2022-01092 (Finaled); BLD2022-03130 (Finaled); BLD2022-04680 (Finaled); BLD2023-00752 (Finaled) |  |  |  |  | 8faefd73-d028-45e0-8b57-2c5d46df942d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/24?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25 | 4 building(s) already Completed on this campus
29 | Amazon Parsons Business Park | 6 | Parson Business Park | REZ2023-00028 | REZ2023-00028 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 96.9 | 1876409 | 1096340 | 6 | Planned: 6 | 1096340 | Coles | Yes | PBD | 7891-69-0322 | 14237 DUMFRIES RD | Amazon Parsons Business Park 1 (Planned); Amazon Parsons Business Park 2 (Planned); Amazon Parsons Business Park 3 (Planned); Amazon Parsons Business Park 4 (Planned); Amazon Parsons Business Park 5 (Planned); Amazon Parsons Business Park 6 (Planned) |  |  |  | REZ2023-00028 [Rezoning - Proffer Amendment; Approved; case number]; SPR2026-00338 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00338 (Pending) | f202a52f-d21d-48eb-ab3e-8577eaaaff93 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/33?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
30 | Astrid | 2 | BOCS - ARC | REZ1958-0021 | REZ1958-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 181.29 | 2800000 | 2800000 | 2 | Planned: 2 | 2800000 | Brentsville | Yes | M-1 | 7497-61-8568 | 6201 WELLINGTON RD | Astrid North (Planned); Astrid South (Planned) |  |  |  | SPR2026-00360 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00360 (Pending) | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/127?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
31 | Century Park | 1 | WHEELER SMITH WOOD SOLITE | REZ1969-0021 | REZ1969-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 24.67 | 620000 | 620000 | 1 | Planned: 1 | 620000 | Gainesville | Yes | M-1 | 7597-53-0484 | 7501 CENTURY PARK DR | Century Park - McLane Site (Planned) |  |  |  | SPR2027-00084 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00084 (Pending) | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/563?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
32 | Century Park Phase 2 & 3 | 2 | WHEELER SMITH WOOD SOLITE | REZ1969-0021 | REZ1969-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 27.3 | 416000 | 416000 | 2 | Planned: 2 | 416000 | Gainesville | Yes | M-1 | 7597-54-1893; 7597-54-9420 | 7101 CENTURY PARK DR; 7300 CENTURY PARK DR | Century Park 1 (Planned); Century Park 2 (Planned) |  |  |  | SPR2026-00336 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00336 (Pending) | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/130?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
33 | CorScale Gainesville Crossing | 5 | Gainesville Crossing | REZ2018-00008 | REZ2018-00008; SUP2019-00029 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 129.75 | 1981643 | 1499420 | 5 | Completed: 3; Planned: 2 | 2251851 | Gainesville | No | PBD | 7497-45-3874; 7497-45-9757; 7497-46-2858; 7497-55-7796; 7497-57-7904 | 13710 UNIVERSITY BLVD; 13720 UNIVERSITY BLVD; 13746 UNIVERSITY BLVD; 13750 UNIVERSITY BLVD; 13760 UNIVERSITY BLVD | Corscale Gainesville Crossing 1 (Completed); Corscale Gainesville Crossing 2 (Completed); Corscale Gainesville Crossing 3 (Completed); Corscale Gainesville Crossing 4 (Planned); Corscale Gainesville Crossing 5 (Planned) | BLD2021-08185 (Finaled); BLD2023-02498 (Finaled); BLD2024-07030 (Finaled); BLD2026-04211 (Pending) |  |  | REZ2018-00008 [Rezoning - Mixed Use; Approved; case number]; SPR2024-00358 [Site Plan - Final; Approved; GPIN (building parcel)]; SUP2019-00029 [Special Use Permit - New Application; Withdrawn; case number REZ2018-00008 referenced in description] |  | e84871aa-43c8-4189-9b23-16244c45106e | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/4?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-10-01 | 3 building(s) already Completed on this campus
34 | Devlin Technology Park | 8 | Devlin Technology Park | REZ2022-00022 | REZ2022-00022; CPA2022-00015 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 184.84 | 3530000 | 3530000 | 8 | Planned: 8 | 1783600 | Brentsville | Yes | M-2 | 7496-63-4453 | 9000 DEVLIN RD | Devlin Technology Park A (Planned); Devlin Technology Park B (Planned); Devlin Technology Park C (Planned); Devlin Technology Park D (Planned); Devlin Technology Park E (Planned); Devlin Technology Park F (Planned); Devlin Technology Park G (Planned); Devlin Technology Park H (Planned) |  |  |  | CPA2022-00015 [Comp Plan Amendment (Concurrent with Rezoning); Dismissed; name exact]; REZ2022-00022 [Rezoning - Non-Residential; Approved; case number]; SPR2026-00332 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00332 (Pending) | 323d298e-a0ad-4dc7-accd-f6b27b404c50 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/7?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-10-01
35 | Digital Realty | 2 | BOCS | REZ1958-0021 | REZ1958-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 31.77 | 382892 | 155427 | 2 | Completed: 1; Planned: 1 | 382892 | Brentsville | Yes | M-1 | 7496-07-8757 | 8217 LINTON HALL RD | Digital Realty VA4 (Completed); Digital Realty VA5 (Planned) | BLD2001-04142 (Finaled) |  |  |  |  | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/54?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25 | 1 building(s) already Completed on this campus
36 | DOANE DRIVE - DULLES GLASS | 1 | WHEELER SMITH WOOD SOLITE | REZ1969-0021 | REZ1969-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 6.89 | 242530 | 242530 | 1 | Planned: 1 | 242530 | Gainesville | Yes | M-1 | 7597-42-8878 | 7610 DOANE DR | DOANE DRIVE - DULLES GLASS (Planned) |  |  |  | SPR2027-00047 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00047 (Pending) | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/553?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
37 | Equinix Manassas | 2 | Battlefield Business Park | REZ1999-0038 | REZ1999-0038; REZ1998-0027 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 9.78 | 284472 | 174672 | 2 | Completed: 1; Planned: 1 | 284472 | Gainesville | Yes | PBD | 7697-47-2201; 7697-47-7005 | 7200 INFANTRY RIDGE RD; 7400 INFANTRY RIDGE RD | Equinix Manassas DC14 (Completed); Equinix Manassas DC19 (Planned) | BLD2006-05319 (Finaled); BLD2027-00758 (Planned) |  |  | SPR2027-00006 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00006 (Pending) | 8c7bc511-c750-4e31-b1ca-f6237f2ac2e8 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/44?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25 | 1 building(s) already Completed on this campus
38 | Exter Property Group | 0 | Linden | REZ1987-0015 | REZ1987-0015 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 12.97 | 155610 | 155610 |  |  |  | Gainesville | Yes | M-2 | [8 empty] | 5645e435-f3f1-4665-bfb2-9cf6f459cc3d | Build_Out_Analysis/10 (campuses) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/122?f=html | 2026-09-25
39 | Gainesville RLC Data Center | 1 | ATLANTIC RESEARCH | REZ1958-0021 | REZ1958-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 12.71 | 989867 | 989867 | 1 | Planned: 1 | 989867 | Brentsville | Yes | M-1 | 7497-14-5061 | 5547 WELLINGTON RD | Gainesville RLC (Planned) |  |  |  | SPR2025-00022 [Site Plan - Final; Approved; GPIN (building parcel)] |  | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/64?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
40 | Gainesville Tech Park Piney Branch | 2 | Gainesville Tech Park | REZ2020-00011 | REZ2020-00011 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 52.69 | 343402 | 343402 | 2 | Planned: 2 | 991418 | Brentsville | Yes | M-2 | 7496-68-8838 | 8101 PINEY BRANCH LN; 8121 PINEY BRANCH LN | Piney Branch 1 (Planned); Piney Branch 2 (Planned) |  |  |  | REZ2020-00011 [Rezoning - Non-Residential; Approved; case number] |  | 01fffe17-1fdc-46e3-bd5c-f5795320e7e6 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/43?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
41 | Gainesville West | 2 | BOCS-ARC | REZ1958-0021 | REZ1958-0021; SUP2023-00005 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 58.3 | 694020 | 694020 | 2 | Planned: 2 | 438895 | Brentsville | Yes | M-1 | 7497-32-5305 | 13225 SKYLARK VIEW WAY; 13235 SKYLARK VIEW WAY | Amazon AWS IAD A (Planned); Amazon AWS IAD B (Planned) | BLD2026-05277 (Pending); BLD2027-01391 (Planned) |  |  | SUP2023-00005 [Special Use - Modification to Development Standards; Withdrawn; name exact] |  | 7b3b0a5f-c395-47c0-99c0-eb53f411acb3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/81?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
42 | Hansen Farm North | 1 | LACY | REZ1958-0034 | REZ1958-0034 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 12.16 | 311000 | 311000 | 1 | Planned: 1 | 224900 | Brentsville | Yes | M-1 | 7597-11-2534 | 7751 WELLINGFORD DR | Hansen Farm North (Planned) |  |  |  | SPR2026-00153 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00153 (Pending) | ce26192c-ef81-4bfe-87c3-346eed0658ae | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/65?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
43 | Hansen Farm South | 1 | CANNON | REZ1990-0076 | REZ1990-0076 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 33.36 | 228140 | 228140 | 1 | Planned: 1 | 228140 | Brentsville | Yes | M-1 | 7497-80-5986 | 7800 PINEY BRANCH LN BRISTOW, VA 20136 | Hansen Farm South (Planned) |  |  |  | SPR2026-00161 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00161 (Pending) | 7ae84689-4196-4d5c-b2f2-2be2a4cac4ff | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/68?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
44 | Hornbaker Road | 1 | Hornbaker Road | REZ2025-00014 | REZ2025-00014; SUP2025-00016; REZ2019-00032 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 20.85 | 435760 | 435760 | 1 | Planned: 1 | 435760 | Brentsville | No | M-2 | 7596-81-5396 | 9001 HORNBAKER RD | Hornbaker Road 2 (Planned) |  |  | SUP2025-00016 [SUP; ACTIVE; approved 2026-03-02] | REZ2019-00032 [Rezoning - Proffer Amendment; Approved; name exact]; REZ2025-00014 [Rezoning - Non-Residential; Approved; case number]; SUP2025-00016 [Special Use Permit - New Application; Approved; case number REZ2025-00014 referenced in description] |  | a0b0e2d0-2ccb-47b1-ab3f-3275db071d01 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); Planning/Zoning/6 (use permits); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/48?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
45 | Innovation on the Parkway | 1 | Innovation on the Parkway PRA | REZ2023-00001 | REZ2023-00001 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 17.73 | 576952 | 576952 | 1 | Planned: 1 | 576952 | Brentsville | Yes | PBD | 7695-09-7902 | 11101 UNIVERSITY BLVD | Innovation on the Parkway (Planned) |  |  |  | REZ2023-00001 [Rezoning - Proffer Amendment; Approved; case number]; SPR2025-00339 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2025-00339 (Pending) | 005eaa9c-a822-4dad-b14e-35d804a4f532 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/25?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
46 | Iron Mountain | 9 | KH Data Capital Development | REZ2021-00022 | REZ2021-00022; REZ2024-00041 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 145.2 | 1953604 | 342028 | 9 | Completed: 8; Planned: 1 | 2179578 | Brentsville | Yes | M-2 PBD | 7596-47-5780; 7596-55-9338; 7596-56-1578; 7596-57-4735; 7596-64-6285; 7596-64-9220; 7596-66-0725; 7596-66-8266 | 11451 ELEVATE DR; 11530 ELEVATE DR 100; 11580 HAYDEN RD; 11600 HAYDEN RD; 11640 HAYDEN RD; 11660 HAYDEN RD; 11680 HAYDEN RD; 7745 WELLINGTON RD; 8330 BETHLEHEM RD | Iron Mountain Data Center VA-1 (Completed); Iron Mountain Data Center VA-10 (Completed); Iron Mountain Data Center VA-2 (Completed); Iron Mountain Data Center VA-3 (Completed); Iron Mountain Data Center VA-4 (Completed); Iron Mountain Data Center VA-5 (Completed); Iron Mountain Data Center VA-6 (Completed); Iron Mountain Data Center VA-7 (Completed); Iron Mountain Data Center VA-8/9 (Planned) | <Null> (Planned); BLD2017-00581 (Finaled); BLD2018-04430 (Finaled); BLD2023-00509 (Finaled); BLD2023-03506 (Finaled); BLD2023-03508 (Finaled); BLD2023-05363 (Finaled); BLD2024-02696 (Finaled); BLD2024-02971 (Finaled) |  |  | REZ2021-00022 [Rezoning - Non-Residential; Approved; case number]; REZ2024-00041 [Rezoning - Mixed Use; Approved; case number] |  | 354103e8-94d2-4b21-951f-d2daa367973a | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/15?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25 | 8 building(s) already Completed on this campus
47 | Iron Mountain Manassas Point | 3 | Manassas Point PRA | REZ2024-00001 | REZ2024-00001 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 39.92 | 5818876 | 1062501 | 3 | Planned: 3 | 1740105 | Gainesville | Yes | M-1 | 7596-79-3589; 7596-89-0058 | 11441 CONNECTIVITY DR; 11451 CONNECTIVITY DR; 11461 CONNECTIVITY DR | Iron Mountain Manassas Point DC1 (Planned); Iron Mountain Manassas Point DC2 (Planned); Iron Mountain Manassas Point DC3 (Planned) |  |  |  | REZ2024-00001 [Rezoning - Proffer Amendment; Approved; case number] |  | 112446d3-3458-4c10-9081-42d87805d421 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/41?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
48 | Manassas Data Center | 1 | STONECREST | REZ1989-0038 | REZ1989-0038; CPA2026-00016; SUP2023-00034 | Approved / Planned | Planned | Pending |  | Rule 3: campus ProjectStatus Planned | 30.48 | 460740 | 460740 | 1 | Planned: 1 | 460740 | Brentsville | Yes | M-2 | 7497-03-2210 | 3555 WELLINGTON CENTER CIR | Manassas Data Center (Planned) |  | CPA2026-00016 [CPA; Pending; name prefix (unique) (companion case, not keyword)]; SUP2023-00034 [SUP; Pending; name prefix (unique) (companion case, not keyword)] |  | PLT2016-00058 [Plat Subdivision; Approved; name prefix (unique)]; SPR2021-00004 [Site Plan - Administrative Review; Approved; name prefix (unique)]; SPR2024-00026 [Site Plan - Final; Approved; name prefix (unique)]; SPR2026-00022 [Site Plan - Grading/Preconstruction Plan; Approved; name prefix (unique)]; SPR2026-00221 [Site Plan - Final; Pending; GPIN (building parcel)]; SPR2027-00022 [Site Plan - Revision; Pending; name prefix (unique)] | SPR2026-00221 (Pending); SPR2027-00022 (Pending) | d4cb066c-32c2-427f-8d02-42b4565dc4c0 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/72?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
49 | Manassas Tech Center | 0 | Manassas Tech Center | REZ2025-00032 | REZ2025-00032 | Approved / Planned | Pending |  | Approved | Campus layer says Pending but ePortal case REZ2025-00032 is Approved (county data conflict) | 5.99 |  | 0 |  |  |  | Brentsville | Yes | PBD PMD | [6 empty] | REZ2025-00032 [Rezoning - Mixed Use; Approved; case number] |  | 9e428798-9025-467d-99e6-391841e4b94e | Build_Out_Analysis/10 (campuses); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/116?f=html ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
50 | Manassas Tech Park II South | 1 | DWOSKIN | REZ1985-0048 | REZ1985-0048 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 30 | 198500 | 198500 | 1 | Planned: 1 | 198500 | Brentsville | Yes | M/T M-2 | 7595-59-2712 | 9320 INDUSTRIAL CT | Manassas Tech Park II South (Planned) |  |  |  | SPR2026-00406 [Site Plan - Final; Awaiting Fees; GPIN (building parcel)] | SPR2026-00406 (Awaiting Fees) | 590d32cd-30f2-4381-a845-2669247e45e0 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/135?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
51 | Manassas Tech Park North | 2 | DWOSKIN | REZ1985-0048 | REZ1985-0048 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 21.17 | 340000 | 340000 | 2 | Planned: 2 | 340000 | Brentsville | Yes | M/T | 7595-49-8655; 7596-50-2719 | 9250 INDUSTRIAL CT; 9251 INDUSTRIAL CT | Manassas Tech Park North 1 (Planned); Manassas Tech Park North 2 (Planned) |  |  |  | SPR2026-00196 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00196 (Pending) | 590d32cd-30f2-4381-a845-2669247e45e0 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/70?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
52 | Merritt I-66 Business Park | 4 | LIBBY, LEONA & HOWARD | REZ1981-0015 | REZ1981-0015 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 49.32 | 2144339 | 2144339 | 4 | Planned: 4 | 2144339 | Gainesville | Yes | M-1 | 7597-24-1765; 7597-24-7195; 7597-24-8417; 7597-25-1404 | 7370 MERRITT PARK DR; 7375 MERRITT PARK DR; 7390 MERRITT PARK DR; 7425 MERRITT PARK DR | Merritt I-66 Business Park A (Planned); Merritt I-66 Business Park B (Planned); Merritt I-66 Business Park C (Planned); Merritt I-66 Business Park D (Planned) |  |  |  | SPR2027-00028 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00028 (Pending) | ba7d803c-ad67-4a97-9720-3ef3910c912b | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/137?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
53 | Microsoft Azure Balls Ford Road | 2 | Westview 66 | REZ2019-00025 | REZ2019-00025 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 40.55 | 1145989 | 1145989 | 2 | Planned: 2 | 1132560 | Gainesville | Yes | PBD | 7597-85-1215 | 11320 BALLS FORD RD; 11324 BALLS FORD RD | Microsoft Azure MNZ01 (Planned); Microsoft Azure MNZ02 (Planned) | BLD2024-06291 (Pending) |  |  | REZ2019-00025 [Rezoning - Proffer Amendment; Approved; case number] |  | 17be9cd0-9800-4877-8c96-5520b706db82 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/10?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
54 | Patriot Business Center | 4 | Wheeler Smith Wood Solite | REZ1969-0021 | REZ1969-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 41.13 | 903523 | 534359 | 4 | Planned: 4 | 903523 | Gainesville | Yes | M-1 | 7597-42-1395; 7597-42-1456; 7597-42-2107 | 11800 BREWERS SPRING RD; 11801 BREWERS SPRING RD; 7600 DOANE DR; BREWERS SPRING RD | Amazon AWS IAD-14 (Planned); Amazon AWS IAD-52 (Planned); Amazon AWS IAD-59 (Planned); Patriot Business Center (Planned) |  |  |  | SPR2015-20225 [Site Plan - Asbuilt Plan; Approved; name exact]; SPR2026-00255 [Site Plan - Early Grading Plan; Pending; GPIN (building parcel)]; SPR2026-00365 [Site Plan - Minor; Approved; GPIN (building parcel)] | SPR2026-00255 (Pending) | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/40?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
55 | Premier Business Park | 1 | WHEELER, SMITH, WOOD, SOLITE | REZ1969-0021 | REZ1969-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 29.74 | 500000 | 500000 | 1 | Planned: 1 | 500000 | Gainesville | Yes | M/T | 7597-34-9837 | 11900 BRADY LN | Premier Business Park Bldg A (Planned) |  |  |  | SPR2027-00041 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00041 (Pending) | 06882327-a3cd-4bd2-9646-9f72bd231847 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/552?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
56 | Project Gulfstream | 4 | Great Oak | REZ1987-0021 | REZ1987-0021 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 64.9 | 1238020 | 1238020 | 4 | Planned: 4 | 1238020 | Coles | Yes | M-2 | 7694-68-7035; 7694-69-8742; 7694-78-6585 | 10230 HARRY J PARRISH BLVD; 10231 HARRY J PARRISH BLVD; 10250 HARRY J PARRISH BLVD | Project Gulfstream Bldg A (Planned); Project Gulfstream Bldg B (Planned); Project Gulfstream Bldg C (Planned); Project Gulfstream Bldg D (Planned) | [5 empty] | fcd445a8-af13-446b-b852-86f22fb0ba21 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/59?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
57 | Project Well | 2 | WORSHAM | REZ1979-0021 | REZ1979-0021; REZ2025-00026 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 43.94 | 490970 | 490970 | 2 | Planned: 2 | 490970 | Brentsville | Yes | M-2 | 7496-97-8786; 7596-08-1375 | 6894 WELLINGTON RD; 6898 WELLINGTON RD | Project Well A (Planned); Project Well B (Planned) |  |  |  | REZ2025-00026 [Rezoning - Mixed Use; Withdrawn; case number]; SPR2026-00108 [Site Plan - Final; Closed; GPIN (building parcel)]; SPR2026-00362 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00362 (Pending) | d71293f1-b842-4858-9413-f26d93b2f4c1 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/49?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
58 | Redstone Tech Park Central | 2 | BROAD RUN INDUSTRIAL PARK | REZ1994-0013 | REZ1994-0013 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 4.66 | 28774 | 28774 | 2 | Planned: 2 | 28774 | Brentsville | Yes | M-1 | 7595-67-8821 | 9651 HAWKINS DR MANASSAS, VA 20109 | Redstone 3 (Planned); Redstone 4 (Planned) |  |  |  | SPR2026-00228 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00228 (Pending) | 785e4c31-8a50-4999-a6f0-e0212ab605bd | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/84?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
59 | Redstone Tech Park North | 5 | REDSTONE INDUSTRIAL PARK | PLN2008-00253 | PLN2008-00253; REZ1996-0016; REZ1985-0048 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 66.7 | 1262501 | 1262501 | 5 | Planned: 5 | 1262501 | Brentsville | Yes | M-1 | 7595-69-2101; 7595-69-2565; 7595-69-4800; 7595-78-0192; 7595-88-0593 | 11090 INDUSTRIAL RD; 11124 INDUSTRIAL RD; 11138 INDUSTRIAL RD; 11140 INDUSTRIAL RD; 11144 INDUSTRIAL RD | Redstone Tech Park North A (Planned); Redstone Tech Park North B (Planned); Redstone Tech Park North C (Planned); Redstone Tech Park North D (Planned); Redstone Tech Park North E (Planned) |  |  |  | SPR2026-00299 [Site Plan - Final; Awaiting Fees; name exact] | SPR2026-00299 (Awaiting Fees) | f9e747f6-b26c-4530-a2fc-298b4be7561d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/89?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
60 | Redstone Tech Park South | 2 | ALBRITE PROPERTY | PLN2007-00406 | PLN2007-00406; REZ1998-0006 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 18.56 | 396887 | 396887 | 2 | Planned: 2 | 396887 | Brentsville | Yes | M/T | 7595-77-5466; 7595-78-4035 | 11101 INDUSTRIAL RD; 9512 HORNBAKER RD | Redstone Tech Park South E (Planned); Redstone Tech Park South F (Planned) | [5 empty] | 39bf6af9-497e-4aa4-9660-80eefa23bf0f | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/76?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
61 | Rose East/West | 3 | WELLINGTON BUSINESS PARK | PLN2004-00071 | PLN2004-00071 | Approved / Planned | Planned |  |  | Rule 3: campus ProjectStatus Planned | 34.8 | 622186 | 622186 | 3 | Planned: 3 | 868254 | Brentsville | Yes | M/T | 7596-09-7967 | 6895 WELLINGTON RD; 7911 MERRIFIELD GARDEN WAY MANASSAS, VA | Rose East A (Planned); Rose East B (Planned); Rose West (Planned) | [5 empty] | 1f3ea70c-725c-49a2-8f29-2492ed6a5e27 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/66?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) | 2026-09-25
62 | Stack Northern Virginia NVA05 | 1 | Stoneview | REZ2023-00026 | REZ2023-00026 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 12.37 | 326500 | 326500 | 1 | Planned: 1 | 326500 | Brentsville | Yes | M-2 | 7696-33-1105 | 8671 WELLINGTON RD | Stack Northern Virginia NVA05E (Planned) |  |  |  | REZ2023-00026 [Rezoning - Non-Residential; Approved; case number] |  | 3f012be5-4a81-4341-8710-e239efdb3b1e | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/18?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
63 | Sudley Manor North | 1 | 11951 Sudley Manor Drive | REZ2020-00010 | REZ2020-00010 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 19.27 | 417960 | 417960 | 1 | Planned: 1 | 417960 | Brentsville | Yes | PBD | 7596-43-9061 | 11950 SUDLEY MANOR DR | Sudley Manor North (Planned) |  |  |  | REZ2020-00010 [Rezoning - Non-Residential; Approved; case number]; SPR2027-00078 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2027-00078 (Pending) | c31952ca-2934-4acc-ab29-9db4ec01e339 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/562?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
64 | Wellington Glen Technology Park | 1 | Wellington Glen Technology Park | REZ2024-00018 | REZ2024-00018 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 27.73 | 673198 | 673198 | 1 | Planned: 1 | 475000 | Brentsville | Yes | PMD | 7596-54-4132 | 11750 STONE CROP DR | Wellington Glen Technology Park (Planned) |  |  |  | REZ2024-00018 [Rezoning - Proffer Amendment; Approved; case number]; SPR2026-00052 [Site Plan - Grading/Preconstruction Plan; Approved; GPIN (building parcel)]; SPR2026-00138 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00138 (Pending) | 3698201f-36be-463f-bc8c-a11881726c77 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/20?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
65 | Yondr Bristow | 4 | Aura Development | REZ2017-00023 | REZ2017-00023 | Approved / Planned | Planned |  | Approved | Rule 3: campus ProjectStatus Planned | 253.56 | 1068986 | 455876 | 4 | Completed: 3; Planned: 1 | 1068986 | Brentsville | Yes | M-2 | 7496-47-2405 | 13040 ROLLINS FORD RD; 13051 ROLLINS FORD RD; 13080 ROLLINS FORD RD; 13085 ROLLINS FORD RD | Yondr Bristow Campus Building 1 (Completed); Yondr Bristow Campus Building 2 (Completed); Yondr Bristow Campus Building 3 (Completed); Yondr Bristow Campus Building 4 (Planned) | BLD2022-03616 (Finaled); BLD2023-01345 (Finaled); BLD2023-04428 (Finaled); BLD2027-01529 (Planned) |  |  | REZ2017-00023 [Rezoning - Mixed Use; Approved; case number] |  | 635db761-516c-4b17-8de3-4283b79a94da | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/11?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-10-01 | 3 building(s) already Completed on this campus
66 | Ashton Data Center | 2 | Ashton Data Center | REZ2022-00031 | REZ2022-00031 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 51.8 | 600000 | 600000 | 2 | Pending: 2 | 600000 | Brentsville | Yes | M/T | 7696-46-3403 | 8552 ASHTON AVE | Ashton Data Center 1 (Pending); Ashton Data Center 2 (Pending) |  | REZ2022-00031 [REZ; Pending; case number] |  | REZ2022-00031 [Rezoning - Non-Residential; Pending; case number] |  | f322379d-0301-4028-9ba5-e23724a6cb51 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/17?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
67 | Atlantic Funding | 3 | Atlantic Funding Development PRA | REZ2026-00041 | REZ2026-00041; SUP2026-00033 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 61.48 | 601882 | 601882 | 3 | Pending: 3 | 601881 | Potomac | No | M-2 | 8290-03-9812 | 16251 DUMFRIES ROAD | Atlantic Funding 1 (Pending); Atlantic Funding 2 (Pending); Atlantic Funding 3 (Pending) |  | REZ2026-00041 [PRA; Pending; case number]; SUP2026-00033 [SUP; Pending; name exact (companion case, not keyword)] |  | REZ2026-00041 [Rezoning - Proffer Amendment; Pending; case number]; SUP2026-00033 [Special Use Permit - New Application; Pending; GPIN (building parcel)] |  | 0a28badf-2c7c-4bea-bc19-d2b3e102f33d | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/128?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
68 | CloudHQ Manassas Corporate Center (MCC) | 1 | Manassas Corporate Center 8 | REZ2026-00032 | REZ2026-00032 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 22.96 | 860788 | 860788 | 1 | Pending: 1 | 860788 | Coles | Yes | PBD | 7794-06-1635 | AIRMAN AVE | CloudHQ Manassas Corporate Center 8 (Pending) |  | REZ2026-00032 [REZ; Pending; case number] |  | REZ2026-00032 [Rezoning - Mixed Use; Pending; case number] |  | 90ca5774-aab1-4185-a26e-d3aa610f23f4 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/50?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
69 | Gardner Property | 5 | Gardner Property | REZ2023-00018 | REZ2023-00018; SUP2027-00008 | Pending / Under Review | Pending | Under Review | Under Review | Rule 4: campus ProjectStatus Pending + pending-case layer Under Review | 82.57 | 2017100 | 2017100 | 5 | Pending: 5 | 2017100 | Brentsville | No | PBD | 7397-34-3968 | 14414 MCGRAWS CORNER DR | Gardner Property A (Pending); Gardner Property B (Pending); Gardner Property C (Pending); Gardner Property D (Pending); Gardner Property E (Pending) |  | REZ2023-00018 [REZ; Under Review; case number]; SUP2027-00008 [SUP; Under Review; DC keyword; companion of REZ2023-00018 (by project name)] |  | REZ2023-00018 [Rezoning - Non-Residential; Under Review; case number]; SUP2027-00008 [Special Use Permit - New Application; Under Review; case number REZ2023-00018 referenced in description] |  | 54197449-7161-4168-861a-d85676a180a3 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/36?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
70 | Hunter Property | 10 | Hunter Property | REZ2022-00019 | REZ2022-00019; REZ2020-00022 | Pending / Under Review | Pending | Suspended (On-Hold) | Suspended (On-Hold) | Rule 4: campus ProjectStatus Pending + pending-case layer Suspended (On-Hold) | 196.02 | 4010000 | 4010000 | 10 | Pending: 10 | 4010000 | Brentsville | Yes | M-2 | 7496-25-7319; 7496-43-8199 | 8505 NIMBUS PL; 8510 NIMBUS PL; 8525 NIMBUS PL; 8530 NIMBUS PL; 8545 NIMBUS PL; 8550 NIMBUS PL; 8570 NIMBUS PL; 8650 NIMBUS PL; 8670 NIMBUS PL; 8675 NIMBUS PL | Hunter Property 1 (Pending); Hunter Property 10 (Pending); Hunter Property 2 (Pending); Hunter Property 3 (Pending); Hunter Property 4 (Pending); Hunter Property 5 (Pending); Hunter Property 6 (Pending); Hunter Property 7 (Pending); Hunter Property 8 (Pending); Hunter Property 9 (Pending) |  | REZ2022-00019 [PRA; Suspended (On-Hold); case number] |  | REZ2020-00022 [Rezoning - Non-Residential; Approved; name exact]; REZ2022-00019 [Rezoning - Proffer Amendment; Suspended (On-Hold); case number]; SPR2022-00287 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2022-00287 (Pending) | 218df4cf-252f-4eee-8ed5-d54f470e1a3f | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/6?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
71 | Madera Farm | 0 | Madera Farm SUP | REZ2025-00007 | REZ2025-00007; SUP2027-00002 | Pending / Under Review |  | REZ2025-00007: Pending; SUP2027-00002: Pending | REZ2025-00007: Pending; SUP2027-00002: Pending | ePortal legislative case open (not in campus layer) | 229.15 | [5 empty] | Brentsville |  |  | 7493-16-9464; 7493-24-3469 | 13213 FARMVIEW RD NOKESVILLE VA 20181; 13250 WARRENTON RD NOKESVILLE VA 20181 |  |  | REZ2025-00007 [REZ; Pending]; SUP2027-00002 [SUP; Pending] |  | REZ2025-00007 [Rezoning - Non-Residential; Pending; applied 2024-09-17]; SUP2027-00002 [Special Use Permit - New Application; Pending; applied 2026-07-31] |  |  | ePortal (EnerGov SelfService); CountyMapper/LandDevelopment/2 (pending cases) | https://egcss.pwcgov.org/SelfService#/home ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
72 | Project Industry | 2 | Project Industry | REZ2025-00003 | REZ2025-00003 | Pending / Under Review | Pending | Deferred | Deferred | Rule 4: campus ProjectStatus Pending + pending-case layer Deferred | 42.2 | 643390 | 643390 | 2 | Pending: 2 | 343516 | Brentsville | Yes | M/T | 7496-58-0951; 7496-58-4088 | 8010 INDUSTRIAL PARK CT; 8021 INDUSTRIAL PARK CT | Project Industry A (Pending); Project Industry B (Pending) |  | REZ2025-00003 [REZ; Deferred; case number] |  | REZ2025-00003 [Rezoning - Non-Residential; Deferred; case number]; SPR2026-00265 [Site Plan - Final; Pending; name exact] | SPR2026-00265 (Pending) | 71a5c10e-0a22-4286-a5c9-b05bff0d3e5f | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/57?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
73 | Six Towers Industrial Park | 2 | Six Towers Industrial Park | REZ2026-00019 | REZ2026-00019; REZ2026-00017 | Pending / Under Review | Pending | Under Review | Under Review | Rule 4: campus ProjectStatus Pending + pending-case layer Under Review | 23.6 | 945252 | 945252 | 2 | Pending: 2 | 945252 | Coles | Yes | PBD | 7892-50-1385 | 7830 SIX TOWERS RD | Six Towers 1 (Pending); Six Towers 2 (Pending) |  | REZ2026-00019 [REZ; Under Review; case number] |  | REZ2026-00017 [Rezoning - Non-Residential; Voided; name exact]; REZ2026-00019 [Rezoning - Mixed Use; Under Review; case number] |  | f32568b2-c8f2-4134-815c-9da3cb62a8f1 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/58?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
74 | Southgate South | 3 | Southgate South REZ & PRA | REZ2026-00044 | REZ2026-00044; SUP2026-00035 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 80.03 | 909000 | 909000 | 3 | Pending: 3 | 909000 | Potomac | No | M-2 | 8190-90-6518 | 16401 DUMFRIES RD | Southgate South 1 (Pending); Southgate South 2 (Pending); Southgate South 3 (Pending) |  | REZ2026-00044 [PRA; Pending; case number]; SUP2026-00035 [SUP; Pending; DC keyword; companion of REZ2026-00044 (by project name)] |  | REZ2026-00044 [Rezoning - Non-Residential; Pending; case number]; SUP2026-00035 [Special Use Permit - New Application; Pending; GPIN (building parcel)] |  | 4f9d38d6-2dd5-44b1-b5c1-cc2aa25e5628 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/132?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
75 | Sudley Manor Drive | 1 | Sudley Manor Drive Amazon Data Services | REZ2026-00039 | REZ2026-00039; REZ2020-00010; REZ2025-00006 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 34.78 | 293236 | 293236 | 1 | Pending: 1 | 293236 | Brentsville | Yes | PBD |  | 11951 SUDLEY MANOR DR MANASSAS, VA 20109 | SUDLEY MANOR DRIVE A (Pending) |  | REZ2026-00039 [PRA; Pending; case number] |  | PLT2023-00071 [Plat Subdivision; Approved; name exact]; REZ2020-00010 [Rezoning - Non-Residential; Approved; case number]; REZ2025-00006 [Rezoning - Non-Residential; Withdrawn; name exact]; REZ2026-00039 [Rezoning - Proffer Amendment; Pending; case number]; SPR2026-00337 [Site Plan - Final; Pending; name exact] | SPR2026-00337 (Pending) | 0c99ba68-b226-48b7-a340-5974eaf7768b | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/112?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
76 | University Business Park | 2 | University Business Park | REZ2023-00019 | REZ2023-00019; REZ1958-0021 | Pending / Under Review | Pending | Pending | Pending | Rule 4: campus ProjectStatus Pending + pending-case layer Pending | 117.21 | 3800000 | 3800000 | 2 | Pending: 2 | 770200 | Brentsville | Yes | M-1 | 7497-43-7416 | 13490 UNIVERSITY BLVD | Microsoft Azure MNZ07 (Pending); Microsoft Azure MNZ08 (Pending) |  | REZ2023-00019 [REZ; Pending; case number] |  | REZ2023-00019 [Rezoning - Non-Residential; Pending; case number]; SPR2023-00349 [Site Plan - Final; Inactive; GPIN (building parcel)]; SPR2026-00377 [Site Plan - Final; Pending; GPIN (building parcel)] | SPR2026-00377 (Pending) | dba835c0-d92e-4f81-aca7-df3546eddf60 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases); ePortal | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/9?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 ¦ https://egcss.pwcgov.org/SelfService#/home | 2026-09-25
77 | Project Mango Phase 4 | 0 | PROJECT MANGO PHASE 4 | SPR2026-00368 | SPR2026-00368; SPR2027-00055 | In Planning Office (site plan in review) |  |  | SPR2026-00368: Pending; SPR2027-00055: Pending | Rule 5: ePortal site plan in review, no campus-layer match | [9 empty] | 7496-47-2505 | 12998 ROLLINS FORD RD BRISTOW VA 20136; 13001 ROLLINS FORD RD BRISTOW VA 20136 |  |  |  |  | SPR2026-00368 [Site Plan - Final; Pending; applied 2026-05-27]; SPR2027-00055 [Site Plan - Early Grading Plan; Pending; applied 2026-08-13] | SPR2026-00368 (Pending); SPR2027-00055 (Pending) |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
78 | Redstone Tech. Park South (site plan SPR2026-00246) | 0 | Redstone Tech. Park South (site plan SPR2026-00246) | SPR2026-00246 | SPR2026-00246 | In Planning Office (site plan in review) |  |  | SPR2026-00246: Pending | Rule 5: ePortal site plan in review, no campus-layer match | [9 empty] | 7595-78-9620 | 9502 HORNBAKER RD MANASSAS VA 20109 |  |  |  |  | SPR2026-00246 [Site Plan - Final; Pending; applied 2026-02-10] | SPR2026-00246 (Pending) |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
79 | Bristow Campus | 0 | Bristow Campus | REZ2022-00030 | REZ2022-00030; SUP2022-00034 | Void / Withdrawn / Denied |  |  | REZ2022-00030: Denied; SUP2022-00034: Denied | All ePortal legislative cases terminal: Denied | [9 empty] | 7595-63-4137 | 11480 NOKESVILLE RD BRISTOW VA 20136 |  |  |  |  | REZ2022-00030 [Rezoning - Non-Residential; Denied; applied 2022-04-21]; SUP2022-00034 [Special Use Permit - New Application; Denied; applied 2022-04-21] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
80 | Compass Data Centers | 17 | Compass Data Centers | REZ2022-00036 | REZ2022-00036 | Void / Withdrawn / Denied | Pending | Suspended (On-Hold) |  | Override: Digital Gateway/Compass REZ voided (plan §5.4; user instruction); county pending-case layer still shows Suspended (On-Hold); building status shown as Denied (user: Digital Gateway denied); original county label kept in Buildings.county_layer_status | 884.19 | 11555200 | 11555200 | 17 | Denied: 17 | 11555206 | Gainesville | No | PBD |  |  | Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied); Compass Data Centers (Denied) |  | REZ2022-00036 [REZ; Suspended (On-Hold); case number] |  |  |  | a3bccddf-fb99-4d00-9e2b-41916f8455aa | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/172?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 | 2026-09-25
81 | Compton Property | 0 | Compton Property | CPA2021-00005 | CPA2021-00005; REZ2021-00019; SUP2021-00030 | Void / Withdrawn / Denied |  |  | CPA2021-00005: Dismissed; REZ2021-00019: Dismissed; SUP2021-00030: Dismissed | All ePortal legislative cases terminal: Dismissed | [9 empty] | 7696-56-8064 | 8750 RIXLEW LN MANASSAS VA 20109 |  |  |  |  | CPA2021-00005 [Comp Plan Amendment (Concurrent with Rezoning); Dismissed; applied 2021-05-27]; REZ2021-00019 [Rezoning - Non-Residential; Dismissed; applied 2021-05-24]; SUP2021-00030 [Special Use Permit - New Application; Dismissed; applied 2021-05-24] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
82 | Digital Gateway North | 12 | Digital Gateway North | REZ2022-00032 | REZ2022-00032 | Denied | Pending | Suspended (On-Hold) |  | Override: Digital Gateway/Compass REZ voided (plan §5.4; user instruction); county pending-case layer still shows Suspended (On-Hold); building status shown as Denied (user: Digital Gateway denied); original county label kept in Buildings.county_layer_status | 534.08 | 7000000 | 7000000 | 12 | Denied: 12 | 6999996 | Gainesville | No | PBD |  |  | Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied); Digital Gateway North (Denied) |  | REZ2022-00032 [REZ; Suspended (On-Hold); case number] |  |  |  | b0fcafed-a7f4-4ea1-8f83-e71a94ebf4f9 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/138?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 | 2026-09-25
83 | Digital Gateway South | 8 | Digital Gateway South | REZ2022-00033 | REZ2022-00033 | Denied | Pending | Suspended (On-Hold) |  | Override: Digital Gateway/Compass REZ voided (plan §5.4; user instruction); county pending-case layer still shows Suspended (On-Hold); building status shown as Denied (user: Digital Gateway denied); original county label kept in Buildings.county_layer_status | 341.5 | 3700000 | 3700000 | 8 | Denied: 8 | 3700000 | Gainesville | No | PBD |  |  | Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied); Digital Gateway South (Denied) |  | REZ2022-00033 [REZ; Suspended (On-Hold); case number] |  |  |  | 1737b24a-1664-4972-b370-c2436b052e63 | Build_Out_Analysis/10 (campuses); Build_Out_Analysis/9 (buildings); CountyMapper/LandDevelopment/2 (pending cases) | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/10/156?f=html ¦ https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/query?where=GPIN IS NOT NULL&outFields=*&f=html (buildings joined spatially) ¦ https://gisweb.pwcva.gov/arcgis/rest/services/CountyMapper/LandDevelopment/MapServer/2 | 2026-09-25
84 | Dulles South Innovation Center | 0 | Dulles South Innovation Center | CPA2026-00012 | CPA2026-00012 | Void / Withdrawn / Denied |  |  | CPA2026-00012: Denied | All ePortal legislative cases terminal: Denied | [9 empty] | 7400-76-0897 | 3460 SANDERS LN CATHARPIN VA 20143 |  |  |  |  | CPA2026-00012 [Comp Plan Amendment (Concurrent with Rezoning); Denied; applied 2026-02-24] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
85 | Gainesville Associates Data Center FAR | 0 | Gainesville Associates Data Center FAR | SUP2019-00041 | SUP2019-00041 | Void / Withdrawn / Denied |  |  | SUP2019-00041: Withdrawn | All ePortal legislative cases terminal: Withdrawn | [9 empty] | 7497-42-4359 | 5945 WELLINGTON RD GAINESVILLE VA 20155 |  |  |  |  | SUP2019-00041 [Special Use Permit - New Application; Withdrawn; applied 2019-02-28] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
86 | John Marshall Commons Technology Park | 0 | John Marshall Commons Technology Park | REZ2021-00003 | REZ2021-00003; SUP2021-00004 | Void / Withdrawn / Denied |  |  | REZ2021-00003: Withdrawn; SUP2021-00004: Withdrawn | All ePortal legislative cases terminal: Withdrawn | [9 empty] | 7397-46-4281 | 14392 JOHN MARSHALL HWY GAINESVILLE VA 20155 |  |  |  |  | REZ2021-00003 [Rezoning - Non-Residential; Withdrawn; applied 2020-07-31]; SUP2021-00004 [Special Use Permit - New Application; Withdrawn; applied 2020-07-31] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
87 | Potomac Technology Park | 0 | Potomac Technology Park | CPA2024-00002 | CPA2024-00002; REZ2022-00015; SUP2022-00016 | Void / Withdrawn / Denied |  |  | CPA2024-00002: Withdrawn; REZ2022-00015: Withdrawn; SUP2022-00016: Withdrawn | All ePortal legislative cases terminal: Withdrawn | [9 empty] | 7991-04-7237 | 14854 DUMFRIES RD MANASSAS VA 20112 |  |  |  |  | CPA2024-00002 [Comp Plan Amendment (Concurrent with Rezoning); Withdrawn; applied 2024-01-24]; REZ2022-00015 [Rezoning - Non-Residential; Withdrawn; applied 2022-01-06]; SUP2022-00016 [Special Use Permit - New Application; Withdrawn; applied 2022-01-06] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)
88 | Quantico Ridge | 0 | Quantico Ridge | REZ2026-00038 | REZ2026-00038; SUP2026-00029 | Void / Withdrawn / Denied |  |  | REZ2026-00038: Withdrawn; SUP2026-00029: Withdrawn | All ePortal legislative cases terminal: Withdrawn | [9 empty] | 7991-04-7237 | 14854 DUMFRIES RD MANASSAS VA 20112 |  |  |  |  | REZ2026-00038 [Rezoning - Mixed Use; Withdrawn; applied 2026-04-28]; SUP2026-00029 [Special Use Permit - New Application; Withdrawn; applied 2026-04-28] |  |  | ePortal (EnerGov SelfService) | https://egcss.pwcgov.org/SelfService#/home |  | Not in campus layer; acreage/GFA/district not in ePortal search fields (blank)

## Buildings
No. | BuildingName | BuildingStatus | campus_name | campus_case | GPIN | Address | GFA | YearBuilt | PlanningCaseNumber | PermitCase | PermitStatus | OCCDate | LastEditDate | OBJECTID | source_url | county_layer_status
1 | Wellington Road East | Planned | 5451 Wellington Road East | REZ1958-0021 | 7497-13-3597 | 5551 WELLINGTON RD GAINESVILLE, VA 20155 | 116550 |  | REZ1958-0021 |  | Planned |  | 2026-04-28 | 242 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/242?f=html | Planned
2 | Wellington Road West | Planned | 5451 Wellington Road West | REZ1958-0021 | 7497-04-7126 | 5451 WELLINGTON RD GAINESVILLE, VA 20155 | 255500 |  | REZ1958-0021 |  | Planned |  | 2026-08-21 | 234 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/234?f=html | Planned
3 | Aligned Data Centers IAD05 | Planned | Aligned Manassas | REZ2019-00022 | 7597-95-8953 | 10920 BALLS FORD RD | 432742 |  |  |  | Planned |  | 2026-04-22 | 75 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/75?f=html | Planned
4 | Amazon Bethlehem Technology Park DC18 | Completed | Amazon Bethlehem Technology Park | REZ2016-00024 | 7596-58-8732 | 8180 BETHLEHEM RD | 211816 | 2017 |  | BLD2017-02845 | Finaled | 2017-10-21 | 2026-08-21 | 14 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/14?f=html | Completed
5 | Amazon Bethlehem Technology Park DC19 | Completed | Amazon Bethlehem Technology Park | REZ2016-00024 | 7596-58-8732 | 8200 BETHLEHEM RD | 148580 | 2017 |  | BLD2016-06361 | Finaled | 2017-05-31 | 2026-08-21 | 15 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/15?f=html | Completed
6 | Amazon Bethlehem Technology Park DC20 | Completed | Amazon Bethlehem Technology Park | REZ2016-00024 | 7596-58-8732 | 8210 BETHLEHEM RD | 211816 | 2017 |  | BLD2017-01263 | Finaled | 2017-08-03 | 2026-08-21 | 16 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/16?f=html | Completed
7 | Amazon Bethlehem Technology Park DC23 | Completed | Amazon Bethlehem Technology Park | REZ2016-00024 | 7596-58-8732 | 8190 BETHLEHEM RD | 147530 | 2020 |  | BLD2018-03269 | Finaled | 2020-05-13 | 2026-08-21 | 13 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/13?f=html | Completed
8 | Amazon Colchester Industrial Park 1 | Planned | Amazon Colchester Industrial Park | REZ2024-00006 | 7991-45-0874 | 14901 DUMFRIES RD | 224173 |  | REZ2024-00006 |  | Planned |  | 2026-04-16 | 134 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/134?f=html | Planned
9 | Amazon Colchester Industrial Park 2 | Planned | Amazon Colchester Industrial Park | REZ2024-00006 | 7991-45-0874 | 14901 DUMFRIES RD | 224173 |  | REZ2024-00006 |  | Planned |  | 2026-04-16 | 132 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/132?f=html | Planned
10 | Amazon AWS IAD-130 | Completed | Amazon Freedom Boulevard | REZ1989-0022 | 7696-21-7764 | 9040 FREEDOM CENTER BLVD | 204211 | 2020 |  | BLD2019-01155 | Finaled | 2020-09-15 | 2026-02-26 | 27 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/27?f=html | Completed
11 | Amazon AWS IAD-131 | Completed | Amazon Freedom Boulevard | REZ1989-0022 | 7696-21-7764 | 9020 FREEDOM CENTER BLVD | 204211 | 2020 |  | BLD2019-04018 | Finaled | 2020-12-01 | 2026-02-26 | 28 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/28?f=html | Completed
12 | Amazon AWS IAD-104 | Completed | Amazon Innovation Drive | PLN2007-00749 | 7695-17-9607 | 9680 INNOVATION DR | 213320 | 2024 | PLN2007-0074 | BLD2022-01092 | Finaled | 2024-01-21 | 2026-04-21 | 20 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/20?f=html | Completed
13 | Amazon AWS IAD-105 | Completed | Amazon Innovation Drive | PLN2007-00749 | 7695-26-4469 | 9700 INNOVATION DR | 223757 | 2024 | PLN2007-0074 | BLD2022-03130 | Finaled | 2024-07-28 | 2026-04-21 | 19 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/19?f=html | Completed
14 | Amazon AWS IAD-106 | Completed | Amazon Innovation Drive | PLN2007-00749 | 7695-26-7645 | 9720 INNOVATION DR | 233757 | 2025 | PLN2007-0074 | BLD2022-04680 | Finaled | 2025-02-19 | 2026-04-21 | 18 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/18?f=html | Completed
15 | Amazon AWS IAD-107 | Completed | Amazon Innovation Drive | PLN2007-00749 | 7695-36-1324 | 9740 INNOVATION DR | 216067 | 2025 | PLN2007-0074 | BLD2023-00752 | Finaled | 2025-05-27 | 2026-04-21 | 17 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/17?f=html | Completed
16 | Amazon AWS IAD-F | Planned | Amazon Innovation Drive | PLN2007-00749 | 7695-17-9607 | 9670 INNOVATION DR | 201000 |  | PLN2007-0074 |  | Planned |  | 2026-08-21 | 233 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/233?f=html | Planned
17 | Amazon AWS IAD-11 | Completed | Amazon Mason King Court | REZ1969-0021 | 7597-62-3841 | 7510 MASON KING CT | 167145 | 2012 |  | BLD2012-03056 | Finaled | 1986-06-03 | 2026-08-21 | 69 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/69?f=html | Completed
18 | Amazon AWS IAD-24 | Completed | Amazon Mason King Court | REZ1969-0021 | 7597-62-3841 | 7610 MASON KING CT | 41786 | 2012 |  | BLD2012-02503 | Finaled | 2012-09-19 | 2026-02-26 | 70 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/70?f=html | Completed
19 | Amazon AWS IAD-7 | Completed | Amazon Mason King Court | REZ1969-0021 | 7597-72-1867 | 7505 MASON KING CT | 167193 | 2012 |  | BLD2009-02929 | Finaled | 2012-09-19 | 2026-02-26 | 67 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/67?f=html | Completed
20 | Amazon AWS IAD 15445 John Marshall | Completed | Amazon Midwood Center | PLN2003-00108 | 7298-41-4524 | 15445 JOHN MARSHALL HWY | 141592 | 2024 |  | BLD2022-07765 | Finaled | 2024-11-04 | 2026-08-21 | 106 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/106?f=html | Completed
21 | Amazon AWS IAD-55 | Completed | Amazon Midwood Center | PLN2003-00108 | 7298-51-5907 | 15395 JOHN MARSHALL HWY | 236082 | 2014 |  | BLD2014-01766 | Finaled | 2014-07-28 | 2026-08-21 | 105 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/105?f=html | Completed
22 | Amazon AWS IAD-64 | Completed | Amazon Midwood Center | PLN2003-00108 | 7298-41-4524 | 15465 JOHN MARSHALL HWY | 147187 | 2017 |  | BLD2016-04280 | Finaled | 2017-10-25 | 2026-08-21 | 107 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/107?f=html | Completed
23 | Amazon AWS IAD-64 Ext | Completed | Amazon Midwood Center | PLN2003-00108 | 7298-41-4524 | 15475 JOHN MARSHALL HWY | 17421 | 2021 |  | BLD2020-04888 | Finaled | 2021-11-25 | 2026-08-21 | 109 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/109?f=html | Completed
24 | Amazon AWS IAD-84 | Completed | Amazon Midwood Center | PLN2003-00108 | 7298-41-4524 | 15455 JOHN MARSHALL HWY | 147187 | 2023 |  | BLD2018-06209 | Finaled | 2023-07-10 | 2026-08-21 | 108 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/108?f=html | Completed
25 | Amazon Parsons Business Park 1 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 171785 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 136 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/136?f=html | Planned
26 | Amazon Parsons Business Park 2 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 227153 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 137 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/137?f=html | Planned
27 | Amazon Parsons Business Park 3 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 227153 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 135 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/135?f=html | Planned
28 | Amazon Parsons Business Park 4 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 227153 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 138 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/138?f=html | Planned
29 | Amazon Parsons Business Park 5 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 227153 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 139 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/139?f=html | Planned
30 | Amazon Parsons Business Park 6 | Planned | Amazon Parsons Business Park | REZ2023-00028 | 7891-69-0322 | 14237 DUMFRIES RD | 15943 |  | REZ2023-00028 |  | Planned |  | 2026-05-04 | 244 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/244?f=html | Planned
31 | Amazon AWS IAD-100 | Completed | Amazon Tanner Way | REZ2018-00002 | 7695-62-8723 | 10321 TANNER WAY | 212017 | 2021 | REZ2018-00002 | BLD2020-00115 | Finaled | 2021-10-13 | 2026-06-10 | 46 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/46?f=html | Completed
32 | Amazon AWS IAD-101 | Completed | Amazon Tanner Way | REZ2018-00002 | 7695-62-8723 | 10301 TANNER WAY | 214796 | 2022 | REZ2018-00002 | BLD2020-04380 | Finaled | 2022-03-07 | 2026-06-10 | 48 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/48?f=html | Completed
33 | Amazon AWS IAD-102 | Completed | Amazon Tanner Way | REZ2018-00002 | 7695-62-8723 | 10281 TANNER WAY | 214796 | 2022 | REZ2018-00002 | BLD2020-05182 | Finaled | 2020-07-13 | 2026-06-10 | 49 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/49?f=html | Completed
34 | Amazon AWS IAD-103 | Completed | Amazon Tanner Way | REZ2018-00002 | 7695-62-8723 | 10261 TANNER WAY | 153582 | 2023 | REZ2018-00002 | BLD2021-00330 | Finaled | 2023-03-12 | 2026-06-10 | 47 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/47?f=html | Completed
35 | Manassas Amazon AWS 139 | Completed | Amazon Thomasson Barn | PLN2007-00535 | 7595-95-6147 | 11200 THOMASSON BARN RD | 149404 | 2019 |  | BLD2019-02581 | Finaled | 2019-11-14 | 2026-10-02 | 35 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/35?f=html | Completed
36 | Manassas Amazon AWS 140 | Completed | Amazon Thomasson Barn | PLN2007-00535 | 7595-95-6147 | 11150 THOMASSON BARN RD | 202626 | 2020 |  | BLD2019-01459 | Finaled | 2020-02-04 | 2026-10-02 | 36 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/36?f=html | Completed
37 | Village Place Technology Park Bldg 1 | Under Construction | Amazon Village Place Technology Park | REZ2020-00024 | 7397-35-8363 | 14435 JOHN MARSHALL HWY | 217917 |  |  | BLD2024-03062 | Issued |  | 2026-08-06 | 100 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/100?f=html | Under Construction
38 | Village Place Technology Park Bldg 2 | Under Construction | Amazon Village Place Technology Park | REZ2020-00024 | 7397-35-5597 | 14455 JOHN MARSHALL HWY | 0 |  |  | BLD2023-07720 | Issued |  | 2026-02-01 | 99 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/99?f=html | Under Construction
39 | Village Place Technology Park Bldg 3 | Under Construction | Amazon Village Place Technology Park | REZ2020-00024 | 7397-36-2834 | 14475 JOHN MARSHALL HWY | 0 |  |  | BLD2023-04861 | Issued |  | 2026-02-01 | 98 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/98?f=html | Under Construction
40 | Village Place Technology Park Bldg 4 | Under Construction | Amazon Village Place Technology Park | REZ2020-00024 | 7397-36-1468 | 14495 JOHN MARSHALL HWY | 0 |  |  | BLD2023-01296 | Issued |  | 2026-02-01 | 97 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/97?f=html | Under Construction
41 | Amazon AWS IAD-73 Manassas | Completed | Amazon Wellington South | REZ1989-0069 | 7596-17-3979 | 7060 WELLINGTON RD | 148580 | 2016 |  | BLD2015-23921 | Finaled | 2016-07-21 | 2026-08-21 | 10 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/10?f=html | Completed
42 | Amazon AWS IAD-74 Manassas | Completed | Amazon Wellington South | REZ1989-0069 | 7596-17-3979 | 7070 WELLINGTON RD | 148580 | 2016 |  | BLD2015-22325 | Finaled | 2016-01-21 | 2026-08-21 | 9 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/9?f=html | Completed
43 | Ashton Data Center 1 | Pending | Ashton Data Center | REZ2022-00031 | 7696-46-3403 | 8552 ASHTON AVE | 300000 |  | REZ2022-00031 |  | Planned |  | 2026-04-21 | 141 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/141?f=html | Pending
44 | Ashton Data Center 2 | Pending | Ashton Data Center | REZ2022-00031 | 7696-46-3403 | 8552 ASHTON AVE | 300000 |  | REZ2022-00031 |  | Planned |  | 2026-04-21 | 162 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/162?f=html | Pending
45 | Astrid North | Planned | Astrid | REZ1958-0021 | 7497-61-8568 | 6201 WELLINGTON RD | 1700000 |  | REZ1958-0021 |  | Planned |  | 2026-05-19 | 251 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/251?f=html | Planned
46 | Astrid South | Planned | Astrid | REZ1958-0021 | 7497-61-8568 | 6201 WELLINGTON RD | 1100000 |  | REZ1958-0021 |  | Planned |  | 2026-05-19 | 252 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/252?f=html | Planned
47 | Atlantic Funding 1 | Pending | Atlantic Funding | REZ2026-00041 | 8290-03-9812 | 16251 DUMFRIES ROAD | 200627 |  | REZ2026-00041 |  | Planned |  | 2026-05-26 | 255 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/255?f=html | Pending
48 | Atlantic Funding 2 | Pending | Atlantic Funding | REZ2026-00041 | 8290-03-9812 | 16251 DUMFRIES ROAD | 200627 |  | REZ2026-00041 |  | Planned |  | 2026-05-26 | 254 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/254?f=html | Pending
49 | Atlantic Funding 3 | Pending | Atlantic Funding | REZ2026-00041 | 8290-03-9812 | 16251 DUMFRIES ROAD | 200627 |  | REZ2026-00041 |  | Planned |  | 2026-05-26 | 253 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/253?f=html | Pending
50 | Century Park - McLane Site | Planned | Century Park | REZ1969-0021 | 7597-53-0484 | 7501 CENTURY PARK DR | 620000 |  | REZ1969-0021 |  | Planned |  | 2026-09-23 | 682 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/682?f=html | Planned
51 | Century Park 1 | Planned | Century Park Phase 2 & 3 | REZ1969-0021 | 7597-54-1893.01 | 7101 CENTURY PARK DR | 252000 |  | REZ1969-0021 |  | Planned |  | 2026-06-03 | 260 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/260?f=html | Planned
52 | Century Park 2 | Planned | Century Park Phase 2 & 3 | REZ1969-0021 | 7597-54-9420.01 | 7300 CENTURY PARK DR | 164000 |  | REZ1969-0021 |  | Planned |  | 2026-06-03 | 259 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/259?f=html | Planned
53 | CloudHQ Manassas Corporate Center 1 | Completed | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-85-3066 | 10880 AIRMAN AVE | 460248 | 2017 |  | BLD2016-05888 | Finaled | 2017-09-13 | 2026-08-21 | 51 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/51?f=html | Completed
54 | CloudHQ Manassas Corporate Center 2 | Completed | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-87-3694 | 10100 HARRY J PARRISH BLVD | 392565 | 2021 |  | BLD2019-02023 | Finaled | 2021-01-04 | 2026-08-21 | 50 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/50?f=html | Completed
55 | CloudHQ Manassas Corporate Center 3 | Planned | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7794-06-4463 | 10740 AIRMAN AVE | 317944 | 0 |  |  | Planned |  | 2026-04-23 | 53 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/53?f=html | Planned
56 | CloudHQ Manassas Corporate Center 4 | Planned | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-96-2732 | 10849 AIRMAN AVE | 252309 | 0 |  |  | Planned |  | 2026-04-23 | 54 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/54?f=html | Planned
57 | CloudHQ Manassas Corporate Center 5 | Planned | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-84-2446 | 10940 AIRMAN AVE | 317944 | 0 |  |  | Planned |  | 2026-04-23 | 55 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/55?f=html | Planned
58 | CloudHQ Manassas Corporate Center 6A | Under Construction | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-95-7303.00 | 10900 AIRMAN AVE | 317944 |  |  | BLD2020-04041 | Issued |  | 2026-02-02 | 52 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/52?f=html | Under Construction
59 | CloudHQ Manassas Corporate Center 6B | Planned | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-95-2326.00 | 10910 AIRMAN AVE | 317944 | 0 |  |  | Planned |  | 2026-04-23 | 130 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/130?f=html | Planned
60 | CloudHQ Manassas Corporate Center 6C | Planned | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-95-2326.00 | 10910 AIRMAN AVE | 317944 | 0 |  |  | Planned |  | 2026-04-23 | 131 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/131?f=html | Planned
61 | CloudHQ Manassas Corporate Center 7 | Under Construction | CloudHQ Manassas Corporate Center (MCC) | PLN2011-00437 | 7694-87-2108 | 10105 HARRY J PARRISH BLVD | 235305 |  | REZ2024-00025 | BLD2026-04432 | Issued |  | 2026-08-13 | 56 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/56?f=html | Under Construction
62 | CloudHQ Manassas Corporate Center 8 | Pending | CloudHQ Manassas Corporate Center (MCC) | REZ2026-00032 | 7794-06-1635 | AIRMAN AVE | 860788 |  | REZ2026-00032 |  | Planned |  | 2026-04-21 | 205 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/205?f=html | Pending
63 | CloudHQ Manassas Data Center 1 | Under Construction | CloudHQ Manassas Data Center (MDC) | REZ2018-00001 | 7695-50-9420 | 10430 HARRY J PARRISH BLVD | 597947 |  | REZ2018-00001 | BLD2025-04928 | Issued |  | 2026-06-17 | 62 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/62?f=html | Under Construction
64 | CloudHQ Manassas Data Center 2 | Under Construction | CloudHQ Manassas Data Center (MDC) | REZ2018-00001 | 7695-50-2882 | 10450 HARRY J PARRISH BLVD | 523151 |  | REZ2018-00001 | BLD2026-01701 | Issued |  | 2026-06-17 | 61 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/61?f=html | Under Construction
65 | CloudHQ Manassas Data Center 3 | Under Construction | CloudHQ Manassas Data Center (MDC) | REZ2018-00001 | 7695-41-6086 | 10470 HARRY J PARRISH BLVD | 523151 |  | REZ2018-00001 | BLD2026-02951 | Issued |  | 2026-07-13 | 265 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/265?f=html | Under Construction
66 | Manassas Amazon AWS 004 | Completed | CloudHQ Manassas Hornbaker | PLN2007-00535 | 7595-96-0662 | 9651 HORNBAKER RD | 247608 | 2010 | PLN2007-00535 | BLD2007-04468 | Finaled | 2010-04-19 | 2026-10-02 | 34 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/34?f=html | Completed
67 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 297 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/297?f=html | Pending
68 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 298 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/298?f=html | Pending
69 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 299 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/299?f=html | Pending
70 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 300 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/300?f=html | Pending
71 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 301 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/301?f=html | Pending
72 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 302 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/302?f=html | Pending
73 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 303 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/303?f=html | Pending
74 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 304 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/304?f=html | Pending
75 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 305 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/305?f=html | Pending
76 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 306 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/306?f=html | Pending
77 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 307 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/307?f=html | Pending
78 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 308 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/308?f=html | Pending
79 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 309 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/309?f=html | Pending
80 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 310 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/310?f=html | Pending
81 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 311 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/311?f=html | Pending
82 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 312 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/312?f=html | Pending
83 | Compass Data Centers | Denied | Compass Data Centers | REZ2022-00036 |  |  | 679718 |  | REZ2022-00036 |  | Planned |  | 2026-08-04 | 313 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/313?f=html | Pending
84 | Corscale Gainesville Crossing 1 | Completed | CorScale Gainesville Crossing | REZ2018-00008 | 7497-46-2858 | 13760 UNIVERSITY BLVD | 482223 | 2024 | REZ2018-00008 | BLD2021-08185 | Finaled | 2024-05-23 | 2026-09-25 | 83 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/83?f=html | Completed
85 | Corscale Gainesville Crossing 2 | Completed | CorScale Gainesville Crossing | REZ2018-00008 | 7497-45-3874 | 13710 UNIVERSITY BLVD | 480200 | 2026 | REZ2018-00008 | BLD2023-02498 | Finaled | 2026-02-10 | 2026-09-25 | 87 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/87?f=html | Completed
86 | Corscale Gainesville Crossing 3 | Completed | CorScale Gainesville Crossing | REZ2018-00008 | 7497-45-9757 | 13720 UNIVERSITY BLVD | 363220 | 2026 | REZ2018-00008 | BLD2024-07030 | Finaled | 2026-06-30 | 2026-10-01 | 84 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/84?f=html | Completed
87 | Corscale Gainesville Crossing 4 | Planned | CorScale Gainesville Crossing | REZ2018-00008 | 7497-55-7796 | 13746 UNIVERSITY BLVD | 326208 |  | REZ2018-00008 | BLD2026-04211 | Pending |  | 2026-09-25 | 86 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/86?f=html | Planned
88 | Corscale Gainesville Crossing 5 | Planned | CorScale Gainesville Crossing | REZ2018-00008 | 7497-57-7904 | 13750 UNIVERSITY BLVD | 600000 |  | REZ2018-00008 |  | Planned |  | 2026-09-25 | 85 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/85?f=html | Planned
89 | DOANE DRIVE - DULLES GLASS | Planned | DOANE DRIVE - DULLES GLASS | REZ1969-0021 | 7597-42-8878 | 7610 DOANE DR | 242530 |  | REZ1969-0021 |  | Planned |  | 2026-09-01 | 678 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/678?f=html | Planned
90 | Devlin Technology Park A | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 127 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/127?f=html | Planned
91 | Devlin Technology Park B | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 126 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/126?f=html | Planned
92 | Devlin Technology Park C | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 124 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/124?f=html | Planned
93 | Devlin Technology Park D | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 122 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/122?f=html | Planned
94 | Devlin Technology Park E | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 125 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/125?f=html | Planned
95 | Devlin Technology Park F | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 123 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/123?f=html | Planned
96 | Devlin Technology Park G | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 121 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/121?f=html | Planned
97 | Devlin Technology Park H | Planned | Devlin Technology Park | REZ2022-00022 | 7496-63-4453 | 9000 DEVLIN RD | 222950 |  |  |  | Planned |  | 2026-04-29 | 128 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/128?f=html | Planned
98 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 277 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/277?f=html | Pending
99 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 278 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/278?f=html | Pending
100 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 279 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/279?f=html | Pending
101 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 280 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/280?f=html | Pending
102 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 281 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/281?f=html | Pending
103 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 290 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/290?f=html | Pending
104 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 291 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/291?f=html | Pending
105 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 292 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/292?f=html | Pending
106 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 293 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/293?f=html | Pending
107 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 294 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/294?f=html | Pending
108 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 295 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/295?f=html | Pending
109 | Digital Gateway North | Denied | Digital Gateway North | REZ2022-00032 |  |  | 583333 |  | REZ2022-00032 |  | Planned |  | 2026-08-04 | 296 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/296?f=html | Pending
110 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 282 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/282?f=html | Pending
111 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 283 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/283?f=html | Pending
112 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 284 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/284?f=html | Pending
113 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 285 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/285?f=html | Pending
114 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 286 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/286?f=html | Pending
115 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 287 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/287?f=html | Pending
116 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 288 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/288?f=html | Pending
117 | Digital Gateway South | Denied | Digital Gateway South | REZ2022-00033 |  |  | 462500 |  | REZ2022-00033 |  | Planned |  | 2026-08-04 | 289 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/289?f=html | Pending
118 | DLR IAD-50 | Under Construction | Digital Realty | REZ2018-00002 | 7695-53-6537.00 | 10050 BRICKYARD WAY | 816374 |  | REZ2018-00002 | BLD2025-02545 | Issued |  | 2026-07-29 | 59 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/59?f=html | Under Construction
119 | DLR IAD-51 | Completed | Digital Realty | REZ2018-00002 | 7695-53-9602.00 | 10051 BRICKYARD WAY | 801246 | 2026 | REZ2018-00002 | BLD2024-02491 | Finaled |  | 2026-07-29 | 58 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/58?f=html | Completed
120 | Digital Realty VA4 | Completed | Digital Realty | REZ1958-0021 | 7496-07-8757 | 8217 LINTON HALL RD | 227465 | 2002 | REZ1958-0021 | BLD2001-04142 | Finaled | 2002-11-05 | 2026-04-30 | 96 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/96?f=html | Completed
121 | Digital Realty VA5 | Planned | Digital Realty | REZ1958-0021 | 7496-07-8757 | 8217 LINTON HALL RD | 155427 |  | REZ1958-0021 |  | Planned |  | 2026-08-21 | 243 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/243?f=html | Planned
122 | Equinix Manassas DC14 | Completed | Equinix Manassas | REZ1999-0038 | 7697-47-7005 | 7400 INFANTRY RIDGE RD | 109800 | 2009 | REZ1999-0038 | BLD2006-05319 | Finaled | 2009-10-22 | 2026-08-14 | 154 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/154?f=html | Completed
123 | Equinix Manassas DC19 | Planned | Equinix Manassas | REZ1999-0038 | 7697-47-2201 | 7200 INFANTRY RIDGE RD | 174672 |  | REZ1998-0027 | BLD2027-00758 | Planned |  | 2026-08-14 | 272 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/272?f=html | Planned
124 | Gainesville RLC | Planned | Gainesville RLC Data Center | REZ1958-0021 | 7497-14-5061 | 5547 WELLINGTON RD | 989867 | 0 | REZ1958-0021 |  | Planned |  | 2026-04-23 | 215 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/215?f=html | Planned
125 | Piney Branch 1 | Planned | Gainesville Tech Park Piney Branch | REZ2020-00011 | 7496-68-8838 | 8101 PINEY BRANCH LN | 495709 |  |  |  | Planned |  | 2026-02-02 | 143 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/143?f=html | Planned
126 | Piney Branch 2 | Planned | Gainesville Tech Park Piney Branch | REZ2020-00011 | 7496-68-8838 | 8121 PINEY BRANCH LN | 495709 |  |  |  | Planned |  | 2026-04-16 | 144 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/144?f=html | Planned
127 | Amazon AWS IAD A | Planned | Gainesville West | REZ1958-0021 | 7497-32-5305 | 13235 SKYLARK VIEW WAY | 244166 |  | REZ1958-0021 | BLD2026-05277 | Pending |  | 2026-09-21 | 114 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/114?f=html | Planned
128 | Amazon AWS IAD B | Planned | Gainesville West | REZ1958-0021 | 7497-32-5305 | 13225 SKYLARK VIEW WAY | 194729 |  | REZ1958-0021 | BLD2027-01391 | Planned |  | 2026-09-21 | 78 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/78?f=html | Planned
129 | Gardner Property A | Pending | Gardner Property | REZ2023-00018 | 7397-34-3968 | 14414 MCGRAWS CORNER DR | 616620 |  |  |  | Planned |  | 2026-09-25 | 140 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/140?f=html | Pending
130 | Gardner Property B | Pending | Gardner Property | REZ2023-00018 | 7397-34-3968 | 14414 MCGRAWS CORNER DR | 350000 |  |  |  | Planned |  | 2026-09-25 | 155 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/155?f=html | Pending
131 | Gardner Property C | Pending | Gardner Property | REZ2023-00018 | 7397-34-3968 | 14414 MCGRAWS CORNER DR | 500000 |  |  |  | Planned |  | 2026-09-25 | 156 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/156?f=html | Pending
132 | Gardner Property D | Pending | Gardner Property | REZ2023-00018 | 7397-34-3968 | 14414 MCGRAWS CORNER DR | 350000 |  |  |  | Planned |  | 2026-09-25 | 157 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/157?f=html | Pending
133 | Gardner Property E | Pending | Gardner Property | REZ2023-00018 | 7397-34-3968 | 14414 MCGRAWS CORNER DR | 200480 |  |  |  | Planned |  | 2026-09-25 | 158 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/158?f=html | Pending
134 | Stack Northern Virginia NVA05A | Completed | George Mason Research Park | REZ2024-00009 | 7696-30-4783 | 9101 FREEDOM CENTER BLVD | 270540 | 2025 | REZ2024-00009 | BLD2023-00562 | Finaled | 2025-07-06 | 2026-04-21 | 32 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/32?f=html | Completed
135 | Stack Northern Virginia NVA05B | Under Construction | George Mason Research Park | REZ2024-00009 | 7696-31-9262 | 9001 FREEDOM CENTER BLVD | 261558 |  | REZ2024-00009 | BLD2025-03129 | Issued | 2025-05-08 | 2026-04-21 | 30 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/30?f=html | Under Construction
136 | Stack Northern Virginia NVA05C | Under Construction | George Mason Research Park | REZ2024-00009 | 7696-41-6854 | 8930 WELLINGTON RD | 179320 |  | REZ2024-00042 | BLD2025-03019 | Issued |  | 2026-04-21 | 31 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/31?f=html | Under Construction
137 | Hansen Farm North | Planned | Hansen Farm North | REZ1958-0034 | 7597-11-2534 | 7751 WELLINGFORD DR | 224900 |  | REZ1958-0034 |  | Planned |  | 2026-08-03 | 216 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/216?f=html | Planned
138 | Hansen Farm South | Planned | Hansen Farm South | REZ1990-0076 | 7497-80-5986 | 7800 PINEY BRANCH LN BRISTOW, VA 20136 | 228140 |  | REZ1990-0076 |  | Planned |  | 2026-04-17 | 220 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/220?f=html | Planned
139 | Hornbaker Road 2 | Planned | Hornbaker Road | REZ2025-00014 | 7596-81-5396 | 9001 HORNBAKER RD | 435760 |  | REZ2025-00014 |  | Planned |  | 2026-04-13 | 204 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/204?f=html | Planned
140 | Hunter Property 1 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8510 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 163 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/163?f=html | Pending
141 | Hunter Property 10 | Pending | Hunter Property | REZ2022-00019 | 7496-43-8199 | 8675 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 172 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/172?f=html | Pending
142 | Hunter Property 2 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8505 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 164 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/164?f=html | Pending
143 | Hunter Property 3 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8570 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 169 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/169?f=html | Pending
144 | Hunter Property 4 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8550 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 168 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/168?f=html | Pending
145 | Hunter Property 5 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8530 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 167 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/167?f=html | Pending
146 | Hunter Property 6 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8525 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 166 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/166?f=html | Pending
147 | Hunter Property 7 | Pending | Hunter Property | REZ2022-00019 | 7496-25-7319 | 8545 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 165 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/165?f=html | Pending
148 | Hunter Property 8 | Pending | Hunter Property | REZ2022-00019 | 7496-43-8199 | 8650 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 170 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/170?f=html | Pending
149 | Hunter Property 9 | Pending | Hunter Property | REZ2022-00019 | 7496-43-8199 | 8670 NIMBUS PL | 401000 |  |  |  | Planned |  | 2026-06-09 | 171 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/171?f=html | Pending
150 | Innovation on the Parkway | Planned | Innovation on the Parkway | REZ2023-00001 | 7695-09-7902 | 11101 UNIVERSITY BLVD | 576952 |  |  |  | Planned |  | 2026-01-22 | 129 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/129?f=html | Planned
151 | Iron Mountain Data Center VA-1 | Completed | Iron Mountain | REZ2021-00022 | 7596-47-5780 | 11680 HAYDEN RD | 165230 | 2017 |  | BLD2017-00581 | Finaled | 2017-09-23 | 2026-08-21 | 1 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/1?f=html | Completed
152 | Iron Mountain Data Center VA-10 | Completed | Iron Mountain | REZ2021-00022 | 7596-64-6285 | 11451 ELEVATE DR | 33574 | 2025 |  | BLD2024-02696 | Finaled | 2025-06-25 | 2026-08-21 | 88 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/88?f=html | Completed
153 | Iron Mountain Data Center VA-2 | Completed | Iron Mountain | REZ2021-00022 | 7596-57-4735 | 11660 HAYDEN RD | 325918 | 2019 |  | BLD2018-04430 | Finaled | 2019-10-23 | 2026-08-21 | 2 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/2?f=html | Completed
154 | Iron Mountain Data Center VA-3 | Completed | Iron Mountain | REZ2021-00022 | 7596-56-1578 | 11640 HAYDEN RD | 389649 | 2024 |  | BLD2023-00509 | Finaled | 2024-09-24 | 2026-08-21 | 3 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/3?f=html | Completed
155 | Iron Mountain Data Center VA-4 | Completed | Iron Mountain | REZ2021-00022 | 7596-66-0725 | 11600 HAYDEN RD | 182032 | 2024 |  | BLD2023-03506 | Finaled | 2025-06-10 | 2026-08-21 | 4 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/4?f=html | Completed
156 | Iron Mountain Data Center VA-5 | Completed | Iron Mountain | REZ2021-00022 | 7596-66-0725 | 11580 HAYDEN RD | 220134 | 2025 |  | BLD2023-03508 | Finaled | 2025-06-10 | 2026-08-21 | 5 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/5?f=html | Completed
157 | Iron Mountain Data Center VA-6 | Completed | Iron Mountain | REZ2021-00022 | 7596-64-9220 | 7745 WELLINGTON RD | 230706 | 2025 |  | BLD2023-05363 | Finaled | 2025-06-17 | 2026-08-21 | 6 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/6?f=html | Completed
158 | Iron Mountain Data Center VA-7 | Completed | Iron Mountain | REZ2021-00022 | 7596-66-8266 | 8330 BETHLEHEM RD | 290307 | 2025 |  | BLD2024-02971 | Finaled | 2025-11-18 | 2026-08-21 | 7 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/7?f=html | Completed
159 | Iron Mountain Data Center VA-8/9 | Planned | Iron Mountain | REZ2021-00022 | 7596-55-9338 | 11530 ELEVATE DR 100 | 342028 | 0 | REZ2024-00041 | <Null> | Planned |  | 2026-08-06 | 8 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/8?f=html | Planned
160 | Iron Mountain Manassas Point DC1 | Planned | Iron Mountain Manassas Point | REZ2024-00001 | 7596-79-3589 | 11461 CONNECTIVITY DR | 580035 | 0 |  |  | Planned |  | 2026-04-23 | 64 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/64?f=html | Planned
161 | Iron Mountain Manassas Point DC2 | Planned | Iron Mountain Manassas Point | REZ2024-00001 | 7596-79-3589 | 11441 CONNECTIVITY DR | 580035 | 0 |  |  | Planned |  | 2026-04-23 | 66 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/66?f=html | Planned
162 | Iron Mountain Manassas Point DC3 | Planned | Iron Mountain Manassas Point | REZ2024-00001 | 7596-89-0058 | 11451 CONNECTIVITY DR | 580035 | 0 |  |  | Planned |  | 2026-04-23 | 65 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/65?f=html | Planned
163 | Manassas Data Center | Planned | Manassas Data Center | REZ1989-0038 | 7497-03-2210 | 3555 WELLINGTON CENTER CIR | 460740 |  | REZ1989-0038 |  | Planned |  | 2026-04-17 | 223 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/223?f=html | Planned
164 | Manassas Tech Center Building A | Under Construction | Manassas Tech Center | REZ2026-00022 | 7596-61-8378.00 | 8890 MIKE GARCIA DR | 220132 |  |  | BLD2025-00144 | Issued |  | 2026-04-21 | 57 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/57?f=html | Under Construction
165 | Manassas Tech Center Building B | Planned | Manassas Tech Center | REZ2026-00022 | 7596-62-9148.00 | 8880 MIKE GARCIA DR | 210329 |  | REZ2026-00022 | BLD2026-06372 | Planned |  | 2026-06-29 | 240 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/240?f=html | Planned
166 | Manassas Tech Center Building C | Planned | Manassas Tech Center | REZ2026-00022 |  | 8881 MIKE GARCIA DR | 256260 |  |  |  | Planned |  | 2026-09-02 | 241 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/241?f=html | Planned
167 | Manassas Tech Park II South | Planned | Manassas Tech Park II South | REZ1985-0048 | 7595-59-2712 | 9320 INDUSTRIAL CT | 198500 |  | REZ1985-0048 |  | Planned |  | 2026-07-16 | 271 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/271?f=html | Planned
168 | Manassas Tech Park North 1 | Planned | Manassas Tech Park North | REZ1985-0048 | 7596-50-2719 | 9251 INDUSTRIAL CT | 170000 |  | REZ1985-0048 |  | Planned |  | 2026-04-17 | 221 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/221?f=html | Planned
169 | Manassas Tech Park North 2 | Planned | Manassas Tech Park North | REZ1985-0048 | 7595-49-8655 | 9250 INDUSTRIAL CT | 170000 |  | REZ1985-0048 |  | Planned |  | 2026-04-17 | 222 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/222?f=html | Planned
170 | Merritt I-66 Business Park A | Planned | Merritt I-66 Business Park | REZ1981-0015 | 7597-25-1404 | 7370 MERRITT PARK DR | 436000 |  | REZ1981-0015 |  | Planned |  | 2026-07-30 | 276 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/276?f=html | Planned
171 | Merritt I-66 Business Park B | Planned | Merritt I-66 Business Park | REZ1981-0015 | 7597-24-1765 | 7390 MERRITT PARK DR | 436000 |  | REZ1981-0015 |  | Planned |  | 2026-07-30 | 275 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/275?f=html | Planned
172 | Merritt I-66 Business Park C | Planned | Merritt I-66 Business Park | REZ1981-0015 | 7597-24-7195 | 7375 MERRITT PARK DR | 633749 |  | REZ1981-0015 |  | Planned |  | 2026-07-30 | 273 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/273?f=html | Planned
173 | Merritt I-66 Business Park D | Planned | Merritt I-66 Business Park | REZ1981-0015 | 7597-24-8417 | 7425 MERRITT PARK DR | 638590 |  | REZ1981-0015 |  | Planned |  | 2026-07-30 | 274 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/274?f=html | Planned
174 | Microsoft Azure MNZ01 | Planned | Microsoft Azure Balls Ford Road | REZ2019-00025 | 7597-85-1215 | 11320 BALLS FORD RD | 566280 |  |  | BLD2024-06291 | Pending |  | 2026-08-13 | 73 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/73?f=html | Planned
175 | Microsoft Azure MNZ02 | Planned | Microsoft Azure Balls Ford Road | REZ2019-00025 | 7597-85-1215 | 11324 BALLS FORD RD | 566280 | 0 |  |  | Planned |  | 2026-04-23 | 74 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/74?f=html | Planned
176 | Microsoft Azure MNZ03 | Under Construction | Microsoft Azure Gainesville Tech Park | REZ2020-00011 | 7496-88-1217 | 13060 HANSEN FARM RD | 312931 |  |  | BLD2023-07492 | Issued |  | 2026-06-09 | 89 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/89?f=html | Under Construction
177 | Microsoft Azure MNZ04 | Planned | Microsoft Azure Gainesville Tech Park | REZ2020-00011 | 7496-88-1217 | 13062 HANSEN FARM RD | 310856 | 0 |  | BLD2025-02384 | Planned |  | 2026-06-17 | 90 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/90?f=html | Planned
178 | Microsoft Azure MNZ05 | Planned | Microsoft Azure Gainesville Tech Park | REZ2020-00011 | 7496-88-1217 | 13064 HANSEN FARM RD | 310856 | 0 |  | <Null> | Planned |  | 2026-06-09 | 91 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/91?f=html | Planned
179 | Microsoft Azure MNZ06 | Planned | Microsoft Azure Gainesville Tech Park | REZ2020-00011 | 7496-88-1217 | 13066 HANSEN FARM RD | 495709 | 0 |  | <Null> | Planned |  | 2026-04-23 | 92 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/92?f=html | Planned
180 | NTT Grove at Gainesville VA10 | Under Construction | NTT Grove at Gainesville | REZ2021-00001 | 7397-56-8403 | 7253 GROVE HILL BLVD | 560942 |  |  | BLD2023-05471 | Issued |  | 2026-06-05 | 101 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/101?f=html | Under Construction
181 | NTT Grove at Gainesville VA11 | Under Construction | NTT Grove at Gainesville | REZ2021-00001 | 7397-56-8403 | 7251 GROVE HILL BLVD | 580498 |  |  | BLD2025-04670 | Issued |  | 2026-06-05 | 104 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/104?f=html | Under Construction
182 | NTT Grove at Gainesville VA12 | Under Construction | NTT Grove at Gainesville | REZ2021-00001 | 7397-56-8403 | 7250 GROVE HILL BLVD | 580724 |  |  | BLD2026-05831 | Issued |  | 2026-09-24 | 102 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/102?f=html | Under Construction
183 | NTT Grove at Gainesville VA13 | Planned | NTT Grove at Gainesville | REZ2021-00001 | 7397-56-8403 | 7151 CATHARPIN RD | 557012 |  |  |  | Planned |  | 2026-06-05 | 103 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/103?f=html | Planned
184 | Amazon AWS IAD-14 | Planned | Patriot Business Center | REZ1969-0021 | 7597-42-2107 | 11801 BREWERS SPRING RD | 199003 |  |  |  | Planned |  | 2026-05-27 | 68 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/68?f=html | Planned
185 | Amazon AWS IAD-52 | Planned | Patriot Business Center | REZ1969-0021 | 7597-42-1456 | 11800 BREWERS SPRING RD | 226123 |  |  |  | Planned |  | 2026-05-27 | 71 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/71?f=html | Planned
186 | Amazon AWS IAD-59 | Planned | Patriot Business Center | REZ1969-0021 | 7597-42-1395 | 7600 DOANE DR | 226132 |  |  |  | Planned |  | 2026-05-27 | 72 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/72?f=html | Planned
187 | Patriot Business Center | Planned | Patriot Business Center | REZ1969-0021 |  | BREWERS SPRING RD | 252265 |  | REZ1969-0021 |  | Planned |  | 2026-05-27 | 226 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/226?f=html | Planned
188 | Premier Business Park Bldg A | Planned | Premier Business Park | REZ1969-0021 | 7597-34-9837 | 11900 BRADY LN | 500000 |  | REZ1969-0021 |  | Planned |  | 2026-08-10 | 677 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/677?f=html | Planned
189 | Amazon AWS IAD A | Under Construction | Project Gainesville | REZ1958-0021 | 7497-41-7199 | 7725 DEACON FALLS DR | 258716 |  | REZ1958-0021 | BLD2022-05922 | Issued |  | 2026-07-17 | 77 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/77?f=html | Under Construction
190 | Amazon AWS IAD B | Under Construction | Project Gainesville | REZ1958-0021 | 7497-41-7199 | 7751 DEACON FALLS DR | 248483 |  | REZ1958-0021 | BLD2024-05622 | Issued |  | 2026-07-13 | 111 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/111?f=html | Under Construction
191 | Amazon AWS IAD C | Under Construction | Project Gainesville | REZ1958-0021 | 7497-41-7199 | 7701 DEACON FALLS DR | 218391 |  | REZ1958-0021 | BLD2026-00592 | Issued |  | 2026-07-13 | 112 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/112?f=html | Under Construction
192 | Amazon AWS IAD D | Under Construction | Project Gainesville | REZ1958-0021 | 7497-41-7199 | 7675 DEACON FALLS DR | 218391 |  | REZ1958-0021 | BLD2026-00593 | Issued |  | 2026-08-06 | 113 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/113?f=html | Under Construction
193 | Project Gulfstream Bldg A | Planned | Project Gulfstream | REZ1987-0021 | 7694-69-8742 | 10250 HARRY J PARRISH BLVD | 373800 |  | REZ1987-0021 |  | Planned |  | 2026-08-14 | 210 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/210?f=html | Planned
194 | Project Gulfstream Bldg B | Planned | Project Gulfstream | REZ1987-0021 | 7694-78-6585 | 10230 HARRY J PARRISH BLVD | 292750 |  | REZ1987-0021 |  | Planned |  | 2026-08-14 | 208 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/208?f=html | Planned
195 | Project Gulfstream Bldg C | Planned | Project Gulfstream | REZ1987-0021 | 7694-68-7035 | 10231 HARRY J PARRISH BLVD | 283790 |  | REZ1987-0021 |  | Planned |  | 2026-08-14 | 209 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/209?f=html | Planned
196 | Project Gulfstream Bldg D | Planned | Project Gulfstream | REZ1987-0021 | 7694-68-7035 | 10231 HARRY J PARRISH BLVD | 287680 |  | REZ1987-0021 |  | Planned |  | 2026-08-14 | 679 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/679?f=html | Planned
197 | Project Industry A | Pending | Project Industry | REZ2025-00003 | 7496-58-4088 | 8021 INDUSTRIAL PARK CT | 171758 |  | REZ2025-00003 |  | Planned |  | 2026-05-05 | 206 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/206?f=html | Pending
198 | Project Industry B | Pending | Project Industry | REZ2025-00003 | 7496-58-0951 | 8010 INDUSTRIAL PARK CT | 171758 |  | REZ2025-00003 |  | Planned |  | 2026-05-05 | 207 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/207?f=html | Pending
199 | Project Well A | Planned | Project Well | REZ1979-0021 | 7596-08-1375 | 6894 WELLINGTON RD | 245485 |  | REZ2025-00026 |  | Planned |  | 2026-07-13 | 160 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/160?f=html | Planned
200 | Project Well B | Planned | Project Well | REZ1979-0021 | 7496-97-8786 | 6898 WELLINGTON RD | 245485 |  | REZ2025-00026 |  | Planned |  | 2026-07-13 | 161 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/161?f=html | Planned
201 | QTS Manassas DC1 | Completed | QTS Manassas 1 | REZ1980-0030 | 7695-48-1668 | 9400 GODWIN DR | 127000 | 2019 | REZ1980-0030 | BLD2018-06634 | Finaled | 2019-03-27 | 2026-07-29 | 23 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/23?f=html | Completed
202 | QTS Manassas DC2 | Completed | QTS Manassas 1 | REZ1980-0030 | 7695-48-5650 | 9420 GODWIN DR | 136228 | 2025 | REZ1980-0030 | BLD2023-04643 | Finaled | 2025-12-28 | 2026-07-29 | 25 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/25?f=html | Completed
203 | QTS Manassas DC3 | Completed | QTS Manassas 1 | REZ1980-0030 | 7695-58-1491 | 9450 GODWIN DR | 269091 | 2024 | REZ1980-0030 | BLD2022-06119 | Finaled | 2024-07-10 | 2026-07-29 | 24 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/24?f=html | Completed
204 | QTS Manassas DC4 | Under Construction | QTS Manassas 1 | REZ1980-0030 | 7695-38-4851 | 9351 FREEDOM CENTER BLVD | 315862 |  | REZ2023-00002 | BLD2025-03459 | Issued |  | 2026-07-29 | 26 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/26?f=html | Under Construction
205 | QTS Manassas DC5 | Completed | QTS Manassas 1 | REZ1980-0030 | 7695-39-0644 | 9301 FREEDOM CENTER BLVD | 308486 | 2023 |  | BLD2021-04300 | Finaled | 2023-04-27 | 2026-08-21 | 22 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/22?f=html | Completed
206 | QTS Manassas DC6 | Under Construction | QTS Manassas 1 | REZ1980-0030 | 7695-47-3376 | 9540 GODWIN DR | 199720 |  | REZ2020-00019 | BLD2024-06788 | Issued |  | 2026-07-29 | 21 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/21?f=html | Under Construction
207 | Redstone 3 | Planned | Redstone Tech Park Central | REZ1994-0013 | 7595-67-8821 | 9651 HAWKINS DR MANASSAS, VA 20109 | 14387 |  | REZ1994-0013 |  | Planned |  | 2026-04-21 | 231 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/231?f=html | Planned
208 | Redstone 4 | Planned | Redstone Tech Park Central | REZ1994-0013 | 7595-67-8821 | 9651 HAWKINS DR MANASSAS, VA 20109 | 14387 |  | REZ1994-0013 |  | Planned |  | 2026-04-21 | 232 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/232?f=html | Planned
209 | Redstone Tech Park North A | Planned | Redstone Tech Park North | PLN2008-00253 | 7595-69-2565 | 11140 INDUSTRIAL RD | 270000 |  | PLN2008-00253 |  | Planned |  | 2026-04-21 | 239 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/239?f=html | Planned
210 | Redstone Tech Park North B | Planned | Redstone Tech Park North | PLN2008-00253 | 7595-69-2101 | 11144 INDUSTRIAL RD | 405000 |  | REZ1985-0048 |  | Planned |  | 2026-04-21 | 238 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/238?f=html | Planned
211 | Redstone Tech Park North C | Planned | Redstone Tech Park North | PLN2008-00253 | 7595-69-4800 | 11138 INDUSTRIAL RD | 248665 |  | REZ1996-0016 |  | Planned |  | 2026-04-21 | 237 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/237?f=html | Planned
212 | Redstone Tech Park North D | Planned | Redstone Tech Park North | PLN2008-00253 | 7595-78-0192 | 11124 INDUSTRIAL RD | 190336 |  | REZ1996-0016 |  | Planned |  | 2026-04-21 | 236 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/236?f=html | Planned
213 | Redstone Tech Park North E | Planned | Redstone Tech Park North | PLN2008-00253 | 7595-88-0593 | 11090 INDUSTRIAL RD | 148500 |  | REZ1996-0016 |  | Planned |  | 2026-04-21 | 235 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/235?f=html | Planned
214 | Redstone Tech Park South E | Planned | Redstone Tech Park South | PLN2007-00406 | 7595-78-4035 | 11101 INDUSTRIAL RD | 200785 |  | REZ1998-0006 |  | Planned |  | 2026-04-17 | 225 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/225?f=html | Planned
215 | Redstone Tech Park South F | Planned | Redstone Tech Park South | PLN2007-00406 | 7595-77-5466 | 9512 HORNBAKER RD | 196102 |  | PLN2007-00406 |  | Planned |  | 2026-04-17 | 224 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/224?f=html | Planned
216 | Rose East A | Planned | Rose East/West | PLN2004-00071 | 7596-09-7967 | 6895 WELLINGTON RD | 356640 |  | PLN2004-00071 |  | Planned |  | 2026-04-17 | 218 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/218?f=html | Planned
217 | Rose East B | Planned | Rose East/West | PLN2004-00071 | 7596-09-7967 | 6895 WELLINGTON RD | 265546 |  | PLN2004-00071 |  | Planned |  | 2026-04-17 | 217 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/217?f=html | Planned
218 | Rose West | Planned | Rose East/West | PLN2004-00071 | 7596-09-7967 | 7911 MERRIFIELD GARDEN WAY MANASSAS, VA | 246068 |  | PLN2004-00071 |  | Planned |  | 2026-04-17 | 219 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/219?f=html | Planned
219 | Six Towers 1 | Pending | Six Towers Industrial Park | REZ2026-00019 | 7892-50-1385 | 7830 SIX TOWERS RD | 472626 |  | REZ2026-00019 |  | Planned |  | 2026-04-21 | 229 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/229?f=html | Pending
220 | Six Towers 2 | Pending | Six Towers Industrial Park | REZ2026-00019 | 7892-50-1385 | 7830 SIX TOWERS RD | 472626 |  | REZ2026-00019 |  | Planned |  | 2026-04-21 | 230 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/230?f=html | Pending
221 | South Point Phase II Building A | Completed | South Point Phase II | REZ2020-00021 | 7596-27-0053 | 8300 BUCKEYE TIMBER DR | 217934 | 2026 |  | BLD2024-01532 | Finaled | 2026-01-07 | 2026-08-21 | 11 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/11?f=html | Completed
222 | South Point Phase II Building B | Under Construction | South Point Phase II | REZ2020-00021 | 7596-16-5979 | 8400 BUCKEYE TIMBER DR | 265000 |  |  | BLD2025-00827 | Issued |  | 2026-02-02 | 12 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/12?f=html | Under Construction
223 | Southgate South 1 | Pending | Southgate South | REZ2026-00044 | 8190-90-6518 | 16401 DUMFRIES RD | 303000 |  | REZ2026-00044 |  | Planned |  | 2026-06-04 | 262 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/262?f=html | Pending
224 | Southgate South 2 | Pending | Southgate South | REZ2026-00044 | 8190-90-6518 | 16401 DUMFRIES RD | 303000 |  | REZ2026-00044 |  | Planned |  | 2026-06-04 | 264 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/264?f=html | Pending
225 | Southgate South 3 | Pending | Southgate South | REZ2026-00044 | 8190-90-6518 | 16401 DUMFRIES RD | 303000 |  | REZ2026-00044 |  | Planned |  | 2026-06-04 | 263 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/263?f=html | Pending
226 | Stack Northern Virginia NVA02A | Completed | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-85-6929 | 9750 HORNBAKER RD | 226862 | 2025 |  | BLD2021-02881 | Finaled | 2025-10-30 | 2026-08-21 | 37 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/37?f=html | Completed
227 | Stack Northern Virginia NVA02B | Completed | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-85-3742 | 9740 HORNBAKER RD | 224652 | 2025 |  | BLD2022-07412 | Finaled | 2025-07-15 | 2026-08-21 | 38 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/38?f=html | Completed
228 | Stack Northern Virginia NVA02C | Completed | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-85-6929 | 9730 HORNBAKER RD | 14387 | 2025 |  | BLD2022-01720 | Finaled | 2025-11-03 | 2026-08-21 | 39 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/39?f=html | Completed
229 | Stack Northern Virginia NVA02D | Completed | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-76-6544.00 | 9590 HORNBAKER RD | 281000 | 2023 |  | BLD2022-00534 | Finaled | 2023-06-08 | 2026-08-21 | 40 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/40?f=html | Completed
230 | Stack Northern Virginia NVA02E | Completed | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-65-9789.00 | 9570 HORNBAKER RD | 259200 | 2024 |  | BLD2023-03853 | Finaled | 2024-08-29 | 2026-08-21 | 42 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/42?f=html | Completed
231 | Stack Northern Virginia NVA02F | Under Construction | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-75-3611 | 9640 HORNBAKER RD | 0 |  |  | BLD2025-01136 | Issued |  | 2026-02-01 | 45 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/45?f=html | Under Construction
232 | Stack Northern Virginia NVA02G | Under Construction | Stack Infrastructure NVA02 Manassas | REZ2019-00028 | 7595-76-2590 | 9530 HORNBAKER RD | 185803 |  | REZ2019-00028 | BLD2024-05348 | Issued |  | 2026-09-01 | 41 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/41?f=html | Under Construction
233 | Stack Northern Virginia NVA02H | Under Construction | Stack Infrastructure NVA02 YFT | REZ2019-00034 | 7595-54-7478 | 10161 LINTON HALL RD | 256280 |  | REZ2019-00034 | BLD2025-06092 | Issued |  | 2026-07-16 | 43 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/43?f=html | Under Construction
234 | Stack Northern Virginia NVA02I | Under Construction | Stack Infrastructure NVA02 YFT | REZ2019-00034 | 7595-54-7478 | 10167 LINTON HALL RD | 256212 |  | REZ2019-00034 | BLD2025-03391 | Issued |  | 2026-07-16 | 44 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/44?f=html | Under Construction
235 | Stack Northern Virginia NVA02J | Under Construction | Stack Infrastructure NVA02 YFT | REZ2019-00034 | 7595-54-7478 | 10155 LINTON HALL RD | 201000 |  | REZ2019-00034 | BLD2026-01905 | Issued |  | 2026-07-16 | 63 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/63?f=html | Under Construction
236 | Stack Northern Virginia NVA05E | Planned | Stack Northern Virginia NVA05 | REZ2023-00026 | 7696-33-1105 | 8671 WELLINGTON RD | 326500 |  | REZ2023-00026 |  | Planned |  | 2026-06-08 | 33 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/33?f=html | Planned
237 | SUDLEY MANOR DRIVE A | Pending | Sudley Manor Drive | REZ2026-00039 |  | 11951 SUDLEY MANOR DR MANASSAS, VA 20109 | 293236 |  | REZ2020-00010 |  | Planned |  | 2026-05-05 | 245 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/245?f=html | Pending
238 | Sudley Manor North | Planned | Sudley Manor North | REZ2020-00010 | 7596-43-9061 | 11950 SUDLEY MANOR DR | 417960 |  | REZ2020-00010 |  | Planned |  | 2026-09-23 | 680 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/680?f=html | Planned
239 | TPC Data Centers | Completed | TPC Data Centers | REZ2024-00008 | 7696-42-1559 | 8819 WELLINGTON RD | 361500 | 2026 | REZ2024-00008 | BLD2024-04783 | Finaled | 2026-07-01 | 2026-07-20 | 29 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/29?f=html | Completed
240 | Microsoft Azure MNZ07 | Pending | University Business Park | REZ2023-00019 | 7497-43-7416 | 13490 UNIVERSITY BLVD | 385100 |  | REZ1958-0021 |  | Planned |  | 2026-08-07 | 116 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/116?f=html | Pending
241 | Microsoft Azure MNZ08 | Pending | University Business Park | REZ2023-00019 | 7497-43-7416 | 13490 UNIVERSITY BLVD | 385100 |  | REZ1958-0021 |  | Planned |  | 2026-08-07 | 118 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/118?f=html | Pending
242 | Verizon Manassas 7777 Infantry Ridge | Completed | Verizon Manassas 7777 Infantry Ridge | REZ1988-0030 | 7697-47-3772 | 7777 INFANTRY RIDGE RD | 227465 | 2002 |  | BLD2026-02975 | Finaled | 2002-06-03 | 2026-08-21 | 153 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/153?f=html | Completed
243 | Wellington Glen Technology Park | Planned | Wellington Glen Technology Park | REZ2024-00018 | 7596-54-4132 | 11750 STONE CROP DR | 475000 |  |  |  | Planned |  | 2026-01-22 | 110 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/110?f=html | Planned
244 | Yondr Bristow Campus Building 1 | Completed | Yondr Bristow | REZ2017-00023 | 7496-47-2405 | 13051 ROLLINS FORD RD | 324580 | 2025 | REZ2017-00023 | BLD2022-03616 | Finaled | 2025-06-23 | 2026-05-29 | 93 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/93?f=html | Completed
245 | Yondr Bristow Campus Building 2 | Completed | Yondr Bristow | REZ2017-00023 | 7496-47-2405 | 13085 ROLLINS FORD RD | 288530 | 2025 | REZ2017-00023 | BLD2023-01345 | Finaled | 2025-06-23 | 2026-05-29 | 94 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/94?f=html | Completed
246 | Yondr Bristow Campus Building 3 | Completed | Yondr Bristow | REZ2017-00023 | 7496-47-2405 | 13040 ROLLINS FORD RD | 288530 | 2026 | REZ2017-00023 | BLD2023-04428 | Finaled | 2026-09-16 | 2026-10-01 | 95 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/95?f=html | Completed
247 | Yondr Bristow Campus Building 4 | Planned | Yondr Bristow | REZ2017-00023 | 7496-47-2405 | 13080 ROLLINS FORD RD | 167346 |  | REZ2017-00023 | BLD2027-01529 | Planned |  | 2026-10-01 | 258 | https://gisweb.pwcva.gov/arcgis/rest/services/Planning/Build_Out_Analysis/MapServer/9/258?f=html | Planned